## README
Irrigation project — stage 2
Source / Fonte | estudo de caso Irrigação (1).docx
Scope / Escopo | 15 activities, 8 risks, 16 mappings.
Decisions / Decisões | Schedule-only case: no cost estimates or targets are supplied; zero cost inputs disable costs and are not estimates. User confirmed R8 -> Material Review 2.4, Triangular impacts for R1/R2/R5/R6/R8, and Normal impacts for R3. Four source activity correlations are documented in Case_Summary but are not simulated. The existing Normal zero-floor policy and shared-risk/independent-impact procedure remain in effect.
Input colors / Cores | Original green input cells, grey optional/calculated cells, yellow required duration/cost parameters and green required mapped impacts retained.
Occurrence / Ocorrência | One occurrence per risk/iteration, applied to its two mappings; magnitudes sampled independently as in the existing model.
Costs / Custos | No cost estimates supplied; all cost values are disabled at zero. Zero outputs are not cost estimates.
Treatments / Tratamentos | No treatment effectiveness supplied; no treatment assumptions invented.
Correlations / Correlações | Four source correlations are retained in Case_Summary but not applied by this model.
Identifiers / Identificadores | Activity IDs such as 2.1 and 2.10 are distinct text identifiers; do not convert them to numbers.
Recalculate / Recalcular | Recalculate and save in Excel after editing, before uploading.
Reference means / Médias | Exponential uses Mean only; Normal uses Mean and SD; three-point impacts follow the user-confirmed distributions.

## Project
1. Project Information
Field | Value | Required? | Data Type | Validation Rule | Example | Simulation Role
Project_ID | IRRIGATION_STAGE_2
Project_Name | Irrigation project — stage 2
Description | Replacement of open channels by pipes and extension to additional properties/outlets.
Time_Unit | weeks
Currency | Not supplied; costs disabled
Simulation_Iterations | 5000
Random_Seed | 42
Target_Duration
Target_Cost
Input_Notes | Schedule-only case: no cost estimates or targets are supplied; zero cost inputs disable costs and are not estimates. User confirmed R8 -> Material Review 2.4, Triangular impacts for R1/R2/R5/R6/R8, and Normal impacts for R3. Four source activity correlations are documented in Case_Summary but are not simulated. The existing Normal zero-floor policy and shared-risk/independent-impact procedure remain in effect.

## Activities
2. Activity Register
Activity_ID | Activity_Name | Predecessors | Duration_Model | Duration_Fixed | Duration_Min | Duration_MostLikely | Duration_Max | Duration_Mean | Duration_SD | Fixed_Cost | Cost_Rate | Cost_Association | Cost_Model | Cost_Fixed | Cost_Min | Cost_MostLikely | Cost_Max | Cost_Mean | Cost_SD
2.1 | Project Planning |  | Normal |  |  |  |  | 2 | 0.5 | 0 | 0 | Fixed only
2.2 | Pipe Design | 2.1 | Triangular |  | 2 | 3 | 4 |  |  | 0 | 0 | Fixed only
2.3 | Material Acquisition | 2.2 | Exponential |  |  |  |  | 1 |  | 0 | 0 | Fixed only
2.4 | Material Review | 2.3 | Triangular |  | 1 | 2 | 3 |  |  | 0 | 0 | Fixed only
2.5 | Excavation for Pipes | 2.2 | Normal |  |  |  |  | 4 | 1 | 0 | 0 | Fixed only
2.6 | Pipe Installation | 2.4,2.5 | Beta-PERT |  | 4 | 5 | 7 |  |  | 0 | 0 | Fixed only
2.7 | Pipe Pressure Testing | 2.6 | Normal |  |  |  |  | 2 | 0.5 | 0 | 0 | Fixed only
2.8 | Quality Inspection | 2.7 | Exponential |  |  |  |  | 1 |  | 0 | 0 | Fixed only
2.9 | Distribution System Connections | 2.8 | Triangular |  | 2 | 3 | 5 |  |  | 0 | 0 | Fixed only
2.10 | Operator Training | 2.8 | Normal |  |  |  |  | 1 | 0.1 | 0 | 0 | Fixed only
2.11 | Initial Monitoring and Maintenance | 2.9,2.10 | Exponential |  |  |  |  | 2 |  | 0 | 0 | Fixed only
2.12 | Project Documentation | 2.11 | Beta-PERT |  | 0.5 | 1 | 1.5 |  |  | 0 | 0 | Fixed only
2.13 | System Commissioning | 2.12 | Normal |  |  |  |  | 1 | 0.3 | 0 | 0 | Fixed only
2.14 | Final Project Report | 2.13 | Exponential |  |  |  |  | 1 |  | 0 | 0 | Fixed only
2.15 | Final Risk Analysis | 2.14 | Normal |  |  |  |  | 1 | 0.2 | 0 | 0 | Fixed only

## Risk_Register
3. Risk Register
Risk_ID | Risk_Name | Risk_Statement | Category | Risk_Type | Probability | Scope | Impact_Type | Trigger_Cause | Owner | Response_Strategy | Response_Action | Status | Impact_Distribution_Default | Notes | Active | Qualitative_Schedule_Impact | Qualitative_Cost_Impact | Assessment_Rationale | Response_Owner | Response_Due_Date | Residual_Probability | Residual_Schedule_Impact | Residual_Cost_Impact | Residual_Acceptance | Residual_Rationale
R1 | Material delivery delays | Material delivery delays; duration impact on 2.3, 2.6; occurrence probability 30%. |  | Threat | 30% | Local | Duration | [5 empty] | Triangular | Triangular selected by user; distribution not named in source. | TRUE
R2 | Pipe design errors | Pipe design errors; duration impact on 2.2, 2.5; occurrence probability 30%. |  | Threat | 30% | Local | Duration | [5 empty] | Triangular | Triangular selected by user; distribution not named in source. | TRUE
R3 | Adverse weather during excavation | Adverse weather during excavation; duration impact on 2.5, 2.6; occurrence probability 20%. |  | Threat | 20% | Local | Duration | [5 empty] | Normal | Normal selected by user; source gives mean/SD but no distribution name. Negative draws use the existing zero floor. | TRUE
R4 | Pressure-test quality problems | Pressure-test quality problems; duration impact on 2.7, 2.8; occurrence probability 40%. |  | Threat | 40% | Local | Duration | [5 empty] | Exponential |  | TRUE
R5 | Communication failures during training | Communication failures during training; duration impact on 2.10, 2.13; occurrence probability 20%. |  | Threat | 20% | Local | Duration | [5 empty] | Triangular | Triangular selected by user; distribution not named in source. | TRUE
R6 | Failed quality inspection | Failed quality inspection; duration impact on 2.8, 2.9; occurrence probability 10%. |  | Threat | 10% | Local | Duration | [5 empty] | Triangular | Triangular selected by user; distribution not named in source. | TRUE
R7 | Lack of qualified installation personnel | Lack of qualified installation personnel; duration impact on 2.6, 2.10; occurrence probability 30%. |  | Threat | 30% | Local | Duration | [5 empty] | Exponential |  | TRUE
R8 | Material review not completed on time | Material review not completed on time; duration impact on 2.4, 2.12; occurrence probability 20%. |  | Threat | 20% | Local | Duration | [5 empty] | Triangular | Triangular selected by user; distribution not named in source. R8 numeric reference 2.15 corrected to named activity 2.4, confirmed by user. | TRUE

## Risk_Activity_Map
4. Risk-Activity Mapping
Risk_ID | Activity_ID | Impact_Type | Distribution | Impact_Fixed | Impact_Min | Impact_MostLikely | Impact_Max | Impact_Mean | Impact_SD
R1 | 2.3 | Duration | Triangular |  | 1 | 2 | 4
R1 | 2.6 | Duration | Triangular |  | 1 | 2 | 4
R2 | 2.2 | Duration | Triangular |  | 1 | 3 | 5
R2 | 2.5 | Duration | Triangular |  | 1 | 3 | 5
R3 | 2.5 | Duration | Normal |  |  |  |  | 1.5 | 1
R3 | 2.6 | Duration | Normal |  |  |  |  | 1.5 | 1
R4 | 2.7 | Duration | Exponential |  |  |  |  | 2
R4 | 2.8 | Duration | Exponential |  |  |  |  | 2
R5 | 2.10 | Duration | Triangular |  | 0.5 | 1 | 2
R5 | 2.13 | Duration | Triangular |  | 0.5 | 1 | 2
R6 | 2.8 | Duration | Triangular |  | 0.5 | 2 | 2.5
R6 | 2.9 | Duration | Triangular |  | 0.5 | 2 | 2.5
R7 | 2.6 | Duration | Exponential |  |  |  |  | 3
R7 | 2.10 | Duration | Exponential |  |  |  |  | 3
R8 | 2.4 | Duration | Triangular |  | 1 | 1.5 | 3
R8 | 2.12 | Duration | Triangular |  | 1 | 1.5 | 3

## Risk_Relationships
5. Optional Risk-Risk Relationships - Advanced / Future Layer
Parent_Risk | Child_Risk | Relationship_Type | Influence_Parameter | Active | Notes

## Validation_Spec
Validation Specification
Area | Rule | Severity | Example Message | Action
Activities | Activity_ID must be unique and nonblank | Error | Duplicate Activity_ID: A03 | Stop simulation
Network | Every predecessor must reference an existing Activity_ID | Error | A07 references unknown predecessor A99 | Stop simulation
Network | Network must be acyclic | Error | Circular relationship detected | Stop simulation
Duration | Duration values must be non-negative | Error | A04 has negative duration | Stop simulation
3-point distributions | Min ≤ Most Likely ≤ Max | Error | A07: Most Likely (12) exceeds Max (9) | Stop simulation
Normal distribution | Mean required; SD must be > 0 | Error | A04: Normal SD must be > 0 | Stop simulation
Risk | Risk_ID must be unique and nonblank | Error | Duplicate Risk_ID: R02 | Stop simulation
Risk | Probability must be between 0 and 1 | Error | R03 probability = 1.30 | Stop simulation
Mapping | Risk_ID must exist in Risk_Register | Error | Mapping references unknown risk R09 | Stop simulation
Mapping | Activity_ID must exist in Activities | Error | R04 maps to unknown activity A18 | Stop simulation
Mapping | Impact parameters must match selected distribution | Error | R02/A04 missing triangular mode | Stop simulation
Optional fields | Blank optional values are permitted | Info | Owner not supplied for R05 | Continue
Text input | Trim leading/trailing spaces where safe | Info | ' A03 ' normalized to 'A03' | Normalize

## Risk_Portrait_Spec
Risk Portrait - Scenario Specification
Scenario | Active Risks | Meaning | ΔMean | ΔP50 | ΔP90
S0 | None | Activity uncertainty only; no tested discrete risks
S1 | R1 | Highest-ranked selected risk
S2 | R1 + R2 | Cumulative addition of second-ranked risk
S3 | R1 + R2 + R3 | Cumulative addition of third-ranked risk
S5 | Top 5 active risks | Concentrated high-priority exposure
ST | All active risks | Total project risk exposure
Interpretation
Simulation control

## Case_Summary
Irrigation project — stage 2
Item | Source / first activity | Second activity | Value / classification | Handling | Notes
Source file | estudo de caso Irrigação (1).docx |  | Scope | Stage 2: 15 activities, 8 risks, 16 mappings | No invented cost or treatment estimates
Confirmed correction | R8 -> 2.4, Material Review |  | User decision | R1/R2/R5/R6/R8 -> Triangular | R3 -> Normal; zero-floor unchanged
Simulation controls | 5000 iterations; seed 42 |  | Origin | Inherited template defaults | Not a case-source claim
Correlations | Stored below for traceability only |  | Model scope | Not applied | No correlation layer added
Source correlation | 2.3 | 2.6 | 0.7 | Not simulated | Activity correlation is not risk-to-risk propagation.
Source correlation | 2.2 | 2.5 | 0.6 | Not simulated | Activity correlation is not risk-to-risk propagation.
Source correlation | 2.7 | 2.8 | 0.5 | Not simulated | Activity correlation is not risk-to-risk propagation.
Source correlation | 2.9 | 2.13 | 0.7 | Not simulated | Activity correlation is not risk-to-risk propagation.

## Risk_Categories
Project risk category reference
Category | Definition

## Risk_Treatments
Treatment scenario assumptions
Risk_ID | Treated_Probability | Duration_Impact_Multiplier | Cost_Impact_Multiplier | Assumption_Rationale

## Case_Assumptions
V2.2 illustrative activity cost assumptions
Activity_ID | Original_Base_Cost | Reference_Duration | Time_Dependent_Share | Fixed_Cost | Cost_Rate | Reference_Total | Basis | Cost_Association
2.1 | 0 | 2 | 0% | 0 | 0 | 0 | No cost data supplied: zero is a disabled-cost placeholder, not an estimate. | Fixed only
2.2 | 0 | 3 | 0% | 0 | 0 | 0 | No cost data supplied: zero is a disabled-cost placeholder, not an estimate. | Fixed only
2.3 | 0 | 1 | 0% | 0 | 0 | 0 | No cost data supplied: zero is a disabled-cost placeholder, not an estimate. | Fixed only
2.4 | 0 | 2 | 0% | 0 | 0 | 0 | No cost data supplied: zero is a disabled-cost placeholder, not an estimate. | Fixed only
2.5 | 0 | 4 | 0% | 0 | 0 | 0 | No cost data supplied: zero is a disabled-cost placeholder, not an estimate. | Fixed only
2.6 | 0 | 5.1667 | 0% | 0 | 0 | 0 | No cost data supplied: zero is a disabled-cost placeholder, not an estimate. | Fixed only
2.7 | 0 | 2 | 0% | 0 | 0 | 0 | No cost data supplied: zero is a disabled-cost placeholder, not an estimate. | Fixed only
2.8 | 0 | 1 | 0% | 0 | 0 | 0 | No cost data supplied: zero is a disabled-cost placeholder, not an estimate. | Fixed only
2.9 | 0 | 3.3333 | 0% | 0 | 0 | 0 | No cost data supplied: zero is a disabled-cost placeholder, not an estimate. | Fixed only
2.10 | 0 | 1 | 0% | 0 | 0 | 0 | No cost data supplied: zero is a disabled-cost placeholder, not an estimate. | Fixed only
2.11 | 0 | 2 | 0% | 0 | 0 | 0 | No cost data supplied: zero is a disabled-cost placeholder, not an estimate. | Fixed only
2.12 | 0 | 1 | 0% | 0 | 0 | 0 | No cost data supplied: zero is a disabled-cost placeholder, not an estimate. | Fixed only
2.13 | 0 | 1 | 0% | 0 | 0 | 0 | No cost data supplied: zero is a disabled-cost placeholder, not an estimate. | Fixed only
2.14 | 0 | 1 | 0% | 0 | 0 | 0 | No cost data supplied: zero is a disabled-cost placeholder, not an estimate. | Fixed only
2.15 | 0 | 1 | 0% | 0 | 0 | 0 | No cost data supplied: zero is a disabled-cost placeholder, not an estimate. | Fixed only