## README
Project Risk Analysis V2.2 input workbook
Purpose | Oriented probabilistic project risk analysis input template.
Workflow | Project → Activities → Risk Register → Risk–Activity Mapping → Validate → Simulate → Risk Portrait → Treatment
Green cells | Core/expected user inputs.
Grey cells | Optional or conditionally required inputs.
Probability | Enter as decimal between 0 and 1 (e.g., 0.30 = 30%).
Duration logic | For three-point distributions: Min/Optimistic ≤ Most Likely ≤ Max/Pessimistic.
Risk occurrence | A risk is sampled once per Monte Carlo iteration, then applied to all mapped activities.
Risk impacts | Consequences are defined in Risk_Activity_Map so the same risk can affect activities differently.
Advanced layer | Risk_Relationships is optional and reserved for later causal/dependency modelling.
Cost model | Fixed_Cost + Cost_Rate × final activity duration + direct mapped risk costs; total floored at zero.
Migration | V2.2 splits each original budget into illustrative fixed/time portions. Fixed_Cost + Cost_Rate × reference duration preserves the original amount; see Case_Assumptions.
Units | Cost_Rate is currency per project time unit. Fixed_Cost is duration-independent; direct risk costs exclude expenses already covered by Cost_Rate.
Register selection | Active=false retains a risk for management but excludes it from simulation. An unselected risk may have blank Probability; active risks require it.
Qualitative scale | User-assessed impact: 1 very low, 2 low, 3 moderate, 4 high, 5 very high. Define project-specific consequences in Assessment_Rationale.
Screening scores | App calculates Probability × impact separately for schedule and cost. Ordinal screening only; no automatic acceptance thresholds.
Response action | Write a concrete action, owner and due date. Existing strategy-only actions are preserved and flagged for completion.
Residual assessment | Residual fields document human assessment; they do not alter simulation inputs. Pending remains until the responsible person decides.
Treatment assumptions | Optional Risk_Treatments rows initialise app controls; blank probability retains original, blank multipliers mean 1. Only selected active risks are treated when Run is pressed.
Treatment dimensions | Duration multiplier changes mapped duration; direct cost multiplier changes mapped cost. Rate-based costs follow final duration automatically.
Category definitions | Risk_Categories preserves project categories. Complete their inclusion criteria; no automatic classification is implied.
Risk relationships | Inactive future layer; no risk propagation in this release.
Risk portrait | Every curve is total project duration for its risk subset. ST includes all active risks. Intermediate scenarios require calculation; ST reuses the main result.
Risk association | Risk importance uses Pearson occurrence/outcome correlation; activity cruciality uses Spearman duration/project-duration correlation. Undefined constant cases display zero.
Category convention | Risk_Categories provides editable working definitions, not an external standard. Choose the primary category and explain overlaps in Notes.
Case source | Case Study of a Residential Building Project.docx: source for the 30-activity/24-risk scenario and original targets. New numeric rates, ratings and treatment effectiveness are illustrative assumptions.
Units assumption | The source specifies generic time/monetary units. Use project time units and monetary units consistently; no real calendar or currency is asserted.
Relative deadlines | Response_Due_Date contains a relative construction milestone because no project start date is supplied. Replace with actual dates once a baseline calendar exists.
Cost basis | Case_Assumptions now calculates live reference duration, cost rate, fixed cost and reference total; Activities links to these results. Green cells are inputs; grey cost cells are calculated.
No double counting | Direct mapped costs are treated as incremental materials, repairs, penalties or emergency expenditure beyond ordinary rate-based resources. Review these boundaries with case experts.
Post-response assumptions | Residual_Probability equals the proposed treated probability; residual severity ratings are subjective expectations, not recalculated simulation results. All acceptance decisions remain Pending.
Opportunities | Higher treated probabilities or multipliers strengthen benefits. Residual opportunity impacts describe expected benefit potential rather than remaining threat severity.
Treatment selection | All 24 risks have proposed treatment assumptions. Only risks selected in the app are treated; there is no automatic implementation or optimisation. Response implementation costs are excluded.
Existing lifecycle statuses | Original Closed statuses and Active=true values are retained as case attributes. Active controls numerical inclusion; Closed does not automatically exclude a risk.
Cost target check | Original activity budgets total 1,057,000 monetary units versus the original 900,000 target. Both are retained; the example already exceeds its target before discrete risks.
Live cost workflow | Select Cost_Association in Activities. Edit Original_Base_Cost and Time_Dependent_Share in Case_Assumptions. Edit duration parameters in Activities. Linked formulas update fixed cost and cost rate.
Fixed only | Fixed only forces Cost_Rate=0 and Fixed_Cost=Original_Base_Cost. The time-dependent share is ignored. A15, A22, A23, A24, A29 and A30 are illustrative fixed-price packages/fees, not verified contract terms.
Cost rate formula | Mixed activity rate = ROUND(original budget × time-dependent share / reference duration, 2). Fixed cost = ROUND(original budget − rate × reference duration, 2). Reference total is fixed cost + rate × reference duration.
Formula and unit checks | A positive time-dependent share requires positive reference duration. Use share 0 or Fixed only for a zero-duration activity. Keep time units consistent.
Direct risk costs | Fixed only removes duration-rate costs; it does not remove explicit additional risk costs from Risk_Activity_Map. Remove or adjust those mappings where the contract transfers that financial exposure.
Saving before upload | Recalculate and save in Excel before uploading after edits. The app reads saved formula results. Do not replace linked cost formulas with typed values unless deliberately leaving this live workflow.
Distribution parameters | Required parameter cells are highlighted for the selected distribution; unused cells remain neutral and their existing contents are retained.
Exponential | Enter an arithmetic Mean > 0. Standard deviation and three-point fields are unused. The distribution is nonnegative and has no finite maximum.
Lognormal and Gamma | Enter arithmetic Mean > 0 and Standard deviation > 0 in the original units. Logarithmic parameters and Gamma shape/scale are derived internally. No finite maximum is imposed.
Optional cost distributions | Leave Cost_Model blank to retain the linked Fixed_Cost workflow. An explicit cost model uses its highlighted Cost_* parameters for the duration-independent component; the existing duration rate and direct risk costs still apply.
Distribution scope | These choices describe activity durations, intrinsic activity costs and mapped impact magnitudes. Risk occurrence probabilities retain their original Fixed/Uniform support.
Reference mean | Reference CPM and linked cost-rate formulas use the entered arithmetic Mean for Exponential, Lognormal and Gamma. Recalculate and save after edits before uploading.

## Project
1. Project Information
Field | Value | Required? | Data Type | Validation Rule | Example | Simulation Role
Project_ID | P01 | Yes | Text | Nonblank | P01 | Simulation identifier
Project_Name | Residential Building Project - V2.2 illustrative case | Yes | Text | Nonblank | Building Project | Reporting/context
Description | Expanded classroom/research demonstration with a broader activity network, threat/opportunity register, and risk–activity exposure map. | No | Text | Optional | Residential construction | Context
Target_Duration | 150 | No | Number | Positive if entered | 120 | Probability of meeting duration target
Target_Cost | 900000 | No | Number | Non-negative if entered | 500000 | Probability of meeting cost target
Simulation_Iterations | 5000 | Yes | Integer | Integer > 0 | 5000 | Monte Carlo run count
Random_Seed | 42 | No | Integer | Integer if entered | 42 | Reproducibility / controlled comparisons
Time_Unit | project time units | Yes | Text | All durations and rates use this unit | days | Cost-rate interpretation
Currency | monetary units | Yes | Text | Use one currency consistently | BRL | Cost interpretation

## Activities
2. Activity Register
Activity_ID | Activity_Name | Predecessors | Duration_Model | Duration_Fixed | Duration_Min | Duration_MostLikely | Duration_Max | Duration_Mean | Duration_SD | Fixed_Cost | Cost_Rate | Cost_Association | Cost_Model | Cost_Fixed | Cost_Min | Cost_MostLikely | Cost_Max | Cost_Mean | Cost_SD
A01 | Mobilization and site establishment |  | Fixed | 5 | 2 | 4 | 8 | 5 | 1.25 | 7800 | 840 | Fixed + time | Fixed | 200 | 80 | 160 | 320 | 200 | 50
A02 | Site survey and setting out | A01 | Triangular | 5 | 2 | 4 | 8 | 5 | 1.25 | 4000.01 | 857.14 | Fixed + time | Triangular | 200 | 80 | 160 | 320 | 200 | 50
A03 | Site clearing and earthworks | A02 | Beta-PERT | 5 | 2 | 4 | 8 | 5 | 1.25 | 13750.02 | 2596.15 | Fixed + time | Beta-PERT | 200 | 80 | 160 | 320 | 200 | 50
A04 | Excavation | A03 | Uniform | 5 | 2 | 4 | 8 | 5 | 1.25 | 9000 | 1800 | Fixed + time | Uniform | 200 | 80 | 160 | 320 | 200 | 50
A05 | Foundation works | A04 | Normal | 5 | 2 | 4 | 8 | 5 | 1.25 | 45500 | 3900 | Fixed + time | Normal | 200 | 80 | 160 | 320 | 200 | 50
A06 | Ground-floor slab | A05 | Exponential | 5 | 2 | 4 | 8 | 5 | 1.25 | 26600 | 2280 | Fixed + time | Exponential | 200 | 80 | 160 | 320 | 200 | 50
A07 | Structural frame – lower floors | A06 | Lognormal | 5 | 2 | 4 | 8 | 5 | 1.25 | 55250 | 5950 | Fixed + time | Lognormal | 200 | 80 | 160 | 320 | 200 | 50
A08 | Structural frame – upper floors | A07 | Gamma | 5 | 2 | 4 | 8 | 5 | 1.25 | 53300 | 5740 | Fixed + time | Gamma | 200 | 80 | 160 | 320 | 200 | 50
A09 | Roof structure and covering | A08 | Fixed | 7 | [5 empty] | 31500 | 1500 | Fixed + time
A10 | External masonry and partitions | A08 | Triangular |  | 7 | 10 | 15 |  |  | 30000 | 1875 | Fixed + time
A11 | Internal partitions | A08 | Beta-PERT |  | 6 | 8 | 12 |  |  | 17600 | 1728 | Fixed + time
A12 | Electrical rough-in | A10,A11 | Normal |  |  |  |  | 8 | 1.5 | 21000 | 1750 | Fixed + time
A13 | Plumbing rough-in | A10,A11 | Fixed | 8 | [5 empty] | 21600 | 1800 | Fixed + time
A14 | HVAC / ventilation rough-in | A10,A11 | Triangular |  | 4 | 6 | 10 |  |  | 18200 | 1470 | Fixed + time
A15 | External doors and windows | A09,A10 | Beta-PERT |  | 4 | 6 | 10 |  |  | 45000 | 0 | Fixed only
A16 | Waterproofing | A09,A13 | Normal |  |  |  |  | 5 | 1 | 15400 | 1320 | Fixed + time
A17 | Internal plastering | A12,A13,A14 | Fixed | 9 | [5 empty] | 22000 | 2000 | Fixed + time
A18 | External rendering / façade | A15 | Triangular |  | 6 | 9 | 14 |  |  | 28799.97 | 1986.21 | Fixed + time
A19 | Floor screed and tiling | A16,A17 | Beta-PERT |  | 6 | 9 | 13 |  |  | 33800.04 | 1985.45 | Fixed + time
A20 | Ceilings | A17 | Normal |  |  |  |  | 6 | 1 | 14300 | 1950 | Fixed + time
A21 | Painting | A18,A19,A20 | Fixed | 9 | [5 empty] | 19000.01 | 2111.11 | Fixed + time
A22 | Electrical fixtures and final connections | A19,A20 | Triangular |  | 4 | 6 | 9 |  |  | 30000 | 0 | Fixed only
A23 | Plumbing fixtures and sanitary installation | A19 | Beta-PERT |  | 4 | 6 | 9 |  |  | 32000 | 0 | Fixed only
A24 | Joinery and cabinetry | A19,A21 | Normal |  |  |  |  | 8 | 1.5 | 42000 | 0 | Fixed only
A25 | External works and drainage | A09 | Fixed | 9 | [5 empty] | 33000.04 | 2444.44 | Fixed + time
A26 | Landscaping | A25 | Triangular |  | 3 | 5 | 8 |  |  | 9900 | 1518.75 | Fixed + time
A27 | Testing and commissioning | A22,A23,A24 | Beta-PERT |  | 4 | 6 | 10 |  |  | 7999.98 | 1894.74 | Fixed + time
A28 | Defect correction / punch list | A21,A24,A27 | Normal |  |  |  |  | 5 | 1 | 7500 | 1500 | Fixed + time
A29 | Final inspection and approvals | A26,A28 | Triangular |  | 2 | 4 | 7 |  |  | 10000 | 0 | Fixed only
A30 | Handover and closeout | A29 | Beta-PERT |  | 1 | 2 | 4 |  |  | 8000 | 0 | Fixed only

## Risk_Register
3. Risk Register
Risk_ID | Risk_Name | Risk_Statement | Category | Risk_Type | Probability | Scope | Impact_Type | Trigger_Cause | Owner | Response_Strategy | Response_Action | Status | Impact_Distribution_Default | Notes | Active | Qualitative_Schedule_Impact | Qualitative_Cost_Impact | Assessment_Rationale | Response_Owner | Response_Due_Date | Residual_Probability | Residual_Schedule_Impact | Residual_Cost_Impact | Residual_Acceptance | Residual_Rationale
R01 | Critical material delivery delay | Critical structural or finishing materials may arrive later than required. | Supply | Threat | 30% | Local | Duration | Supplier disruption / logistics delay | Procurement Manager | Mitigate | Approve material submittals early; place long-lead orders and agree delivery tracking plus a backup supplier. | Open | Fixed | Affects material-dependent activities ¦ V2.2 new assessments and responses are illustrative; original status/Active preserved as scenario attributes. | TRUE | 4 | 3 | ILLUSTRATIVE initial impact assessment: Late critical deliveries can hold foundations, frames or enclosure; delay also increases rate-based costs. | Procurement Manager | Before A05 foundation works | 18% | 3 | 2 | Pending | ILLUSTRATIVE post-response threat exposure; Early procurement reduces delivery interruptions; remaining delays still generate time-related costs. Not a simulation estimate or an approved acceptance decision.
R02 | Higher crew productivity | Experienced crews may complete repetitive work faster than planned. | Operational | Opportunity | 22% | Local | Duration | Learning curve / stable workforce | Site Manager | Exploit | Assign stable experienced crews to repetitive work; use weekly productivity feedback and coaching. | Monitoring | Triangular | Schedule opportunity ¦ V2.2 new assessments and responses are illustrative; original status/Active preserved as scenario attributes. | TRUE | 3 | 2 | ILLUSTRATIVE initial impact assessment: Learning and stable crews can shorten repetitive work and reduce time-dependent resource costs. | Site Manager | Before A07 structural frame | 32% | 4 | 3 | Pending | ILLUSTRATIVE post-response opportunity benefit; Stable crews increase the likelihood and size of schedule benefits; rate-based costs fall with shorter durations. Not a simulation estimate or an approved acceptance decision.
R03 | Adverse weather | Heavy rainfall or extreme weather may interrupt outdoor works. | Environmental | Threat | 35% | Local | Duration | Seasonal weather conditions | Project Manager | Mitigate | Plan weather-sensitive work windows; provide temporary drainage and protective covers. | Monitoring | Beta-PERT | Primarily early and external works ¦ V2.2 new assessments and responses are illustrative; original status/Active preserved as scenario attributes. | TRUE | 4 | 3 | ILLUSTRATIVE initial impact assessment: Rain can interrupt multiple outdoor work packages and extend paid resource occupancy. | Project Manager | Before A03 earthworks | 35% | 3 | 2 | Pending | ILLUSTRATIVE post-response threat exposure; Controls reduce disruption severity; they do not change the probability of adverse weather. Not a simulation estimate or an approved acceptance decision.
R04 | Unforeseen ground conditions | Unexpected soil, groundwater or buried obstruction conditions may be encountered. | Geotechnical | Threat | 18% | Local | Both | Incomplete subsurface information | Civil Engineer | Mitigate | Complete targeted ground investigation, groundwater checks and a foundation contingency method. | Open | Normal | Foundation-stage exposure ¦ V2.2 new assessments and responses are illustrative; original status/Active preserved as scenario attributes. | TRUE | 5 | 5 | ILLUSTRATIVE initial impact assessment: Unknown ground or groundwater can disrupt substructure sequencing and require substantial additional treatment. | Civil Engineer | Before A04 excavation | 18% | 3 | 4 | Pending | ILLUSTRATIVE post-response threat exposure; Investigation does not change ground conditions; preparedness reduces resulting delay and additional ground-treatment costs. Not a simulation estimate or an approved acceptance decision.
R05 | Design change / late clarification | Late design revisions or unresolved details may cause rework or waiting. | Design | Threat | 25% | Local | Both | Client/design coordination changes | Design Manager | Mitigate | Close design RFIs before release; coordinate discipline reviews and enforce change control. | Open | Fixed | Can affect MEP and finishes ¦ V2.2 new assessments and responses are illustrative; original status/Active preserved as scenario attributes. | TRUE | 4 | 4 | ILLUSTRATIVE initial impact assessment: Late design decisions can hold several workstreams and require direct redesign or rework. | Design Manager | Before A07 structural frame | 15% | 3 | 3 | Pending | ILLUSTRATIVE post-response threat exposure; Coordinated released drawings reduce late changes and associated redesign/rework. Not a simulation estimate or an approved acceptance decision.
R06 | Permit or inspection delay | Required authority review or inspection may take longer than planned. | Regulatory | Threat | 15% | Local | Duration | Authority workload / nonconformance | Project Manager | Mitigate | Confirm inspection hold points, submission completeness and booking lead times with the authority. | Closed | Triangular | Late-stage and selected hold points ¦ V2.2 new assessments and responses are illustrative; original status/Active preserved as scenario attributes. | TRUE | 4 | 2 | ILLUSTRATIVE initial impact assessment: Inspection waiting can block hold points or handover; cost exposure is mainly time-related. | Project Manager | Before first mapped inspection hold point | 9% | 3 | 2 | Pending | ILLUSTRATIVE post-response threat exposure; Earlier complete submissions reduce administrative waiting; future-stage inspection exposure remains modelled. Not a simulation estimate or an approved acceptance decision.
R07 | Skilled labour shortage | Specialist or skilled labour may be unavailable when needed. | Resource | Threat | 24% | Local | Both | Labour market constraints | Site Manager | Mitigate | Secure trade labour commitments and cross-train backup crews before mobilisation of specialist trades. | Open | Beta-PERT | Structural, MEP and finishing trades ¦ V2.2 new assessments and responses are illustrative; original status/Active preserved as scenario attributes. | TRUE | 4 | 4 | ILLUSTRATIVE initial impact assessment: Scarce skilled crews can delay structural, MEP and finishing packages and increase recruitment or overtime costs. | Site Manager | Before A07 structural frame | 16% | 3 | 3 | Pending | ILLUSTRATIVE post-response threat exposure; Labour commitments reduce shortages; standby arrangements limit delay and recruitment premiums. Not a simulation estimate or an approved acceptance decision.
R08 | Equipment breakdown | Critical plant or construction equipment may fail unexpectedly. | Equipment | Threat | 16% | Local | Both | Mechanical failure / poor maintenance | Plant Manager | Mitigate | Implement preventive maintenance and reserve replacement plant with agreed call-out times. | Monitoring | Normal | Earthworks and lifting-intensive work ¦ V2.2 new assessments and responses are illustrative; original status/Active preserved as scenario attributes. | TRUE | 3 | 3 | ILLUSTRATIVE initial impact assessment: Plant failure can delay equipment-dependent work and require emergency replacement or repairs. | Plant Manager | Before A03 earthworks | 10% | 2 | 2 | Pending | ILLUSTRATIVE post-response threat exposure; Maintenance reduces breakdown likelihood; replacement arrangements reduce downtime and emergency costs. Not a simulation estimate or an approved acceptance decision.
R09 | Material price escalation | Prices of key materials may exceed the budget assumption. | Commercial | Threat | 28% | Global | Cost | Market inflation / exchange-rate pressure | Commercial Manager | Mitigate | Agree fixed-price supply windows and competitively source key material packages. | Monitoring | Fixed | Cost-only exposure ¦ V2.2 new assessments and responses are illustrative; original status/Active preserved as scenario attributes. | TRUE | 1 | 5 | ILLUSTRATIVE initial impact assessment: Material inflation directly affects the purchase budget; no direct duration impact is mapped (minimum schedule class 1). | Commercial Manager | Before A05 procurement commitments | 28% | 1 | 4 | Pending | ILLUSTRATIVE post-response threat exposure; Market-price changes remain possible; purchasing arrangements reduce the exposed cost increment. Not a simulation estimate or an approved acceptance decision.
R10 | Subcontractor underperformance | A subcontractor may deliver below planned productivity or quality. | Contractor | Threat | 22% | Local | Both | Capacity / management weakness | Contracts Manager | Mitigate | Prequalify subcontractors; agree measurable production targets and an escalation/recovery procedure. | Open | Triangular | Trade-package exposure ¦ V2.2 new assessments and responses are illustrative; original status/Active preserved as scenario attributes. | TRUE | 4 | 4 | ILLUSTRATIVE initial impact assessment: Poor subcontractor production or quality can delay successors and generate recovery expenditure. | Contracts Manager | Before subcontract package award | 14% | 3 | 3 | Pending | ILLUSTRATIVE post-response threat exposure; Capability checks and recovery planning reduce delivery failure and incremental remedial costs. Not a simulation estimate or an approved acceptance decision.
R11 | Quality failure and rework | Work may fail inspection or specification and require correction. | Quality | Threat | 20% | Local | Both | Workmanship / supervision failure | QA/QC Manager | Mitigate | Use approved mock-ups, inspection checklists and sign-off before covering completed work. | Open | Beta-PERT | Broad execution exposure ¦ V2.2 new assessments and responses are illustrative; original status/Active preserved as scenario attributes. | TRUE | 4 | 4 | ILLUSTRATIVE initial impact assessment: Failed work may require removal, replacement and repeat inspections, affecting duration and direct costs. | QA/QC Manager | Before A06 slab and subsequent trade work | 12% | 3 | 3 | Pending | ILLUSTRATIVE post-response threat exposure; First-work approval and inspection reduce defects and limit the scope of direct rework. Not a simulation estimate or an approved acceptance decision.
R12 | Safety incident | A recordable incident may interrupt work and generate investigation/corrective actions. | HSE | Threat | 10% | Global | Both | Unsafe act or condition | HSE Manager | Avoid | Eliminate unsafe work methods where practicable; enforce permits, induction and supervisor checks. | Monitoring | Normal | Higher exposure in structural/external works ¦ V2.2 new assessments and responses are illustrative; original status/Active preserved as scenario attributes. | TRUE | 5 | 5 | ILLUSTRATIVE initial impact assessment: A serious incident may stop work and cause severe human, legal and financial consequences; low probability does not make it acceptable. | HSE Manager | Before A01 mobilisation; maintain throughout works | 5% | 5 | 5 | Pending | ILLUSTRATIVE post-response threat exposure; Controls reduce incident likelihood; severe consequences remain possible and require HSE review regardless of screening score. Not a simulation estimate or an approved acceptance decision.
R13 | Utility service conflict | Existing or planned utilities may conflict with construction or connection works. | Technical | Threat | 12% | Local | Both | Incomplete utility records / coordination | MEP Manager | Mitigate | Verify buried-service records, survey interfaces and agree coordinated service routes. | Closed | Fixed | MEP and external works ¦ V2.2 new assessments and responses are illustrative; original status/Active preserved as scenario attributes. | TRUE | 3 | 3 | ILLUSTRATIVE initial impact assessment: Utility conflicts can block excavation or services and require relocation and reinstatement. | MEP Manager | Before A04 excavation and A12 MEP works | 7% | 2 | 2 | Pending | ILLUSTRATIVE post-response threat exposure; Early utility verification reduces clashes and resulting relocation/rework. Not a simulation estimate or an approved acceptance decision.
R14 | Client decision delay | Delayed approval of samples, finishes or changes may hold downstream work. | Stakeholder | Threat | 20% | Local | Duration | Slow client approvals | Project Manager | Mitigate | Agree a client decision schedule, named approvers and time limits for sample approvals. | Open | Triangular | Finishing activities ¦ V2.2 new assessments and responses are illustrative; original status/Active preserved as scenario attributes. | TRUE | 3 | 2 | ILLUSTRATIVE initial impact assessment: Slow client approvals can hold finishing releases and extend time-dependent costs. | Project Manager | Before A15 doors/windows and finishing releases | 12% | 2 | 2 | Pending | ILLUSTRATIVE post-response threat exposure; Clear deadlines and escalation reduce approval waiting; indirect time costs remain. Not a simulation estimate or an approved acceptance decision.
R15 | Cash-flow / payment delay | Delayed certification or payment may constrain procurement and subcontractor progress. | Financial | Threat | 14% | Global | Both | Payment processing / funding constraints | Commercial Manager | Mitigate | Prepare rolling cash-flow forecasts, submit complete payment claims and arrange a contingency funding facility. | Monitoring | Beta-PERT | Potentially broad project impact ¦ V2.2 new assessments and responses are illustrative; original status/Active preserved as scenario attributes. | TRUE | 4 | 4 | ILLUSTRATIVE initial impact assessment: Cash shortages can affect multiple suppliers and trades and add financing or remobilisation costs. | Commercial Manager | Before A01 mobilisation; review each payment cycle | 10% | 3 | 3 | Pending | ILLUSTRATIVE post-response threat exposure; Payment readiness and liquidity buffers reduce disruption; financing and remobilisation costs remain possible. Not a simulation estimate or an approved acceptance decision.
R16 | Theft or vandalism | Materials, tools or completed work may be lost or damaged. | Security | Threat | 9% | Local | Cost | Site security breach | Site Manager | Mitigate | Secure stores, record material issues and provide controlled access and night surveillance. | Closed | Normal | Storage and finishing exposure ¦ V2.2 new assessments and responses are illustrative; original status/Active preserved as scenario attributes. | TRUE | 1 | 3 | ILLUSTRATIVE initial impact assessment: Theft causes replacement costs; no direct schedule impact is mapped (minimum schedule class 1). | Site Manager | Before A01 site establishment | 5% | 1 | 2 | Pending | ILLUSTRATIVE post-response threat exposure; Security measures reduce loss likelihood and unrecovered replacement costs; no direct schedule consequence is mapped. Not a simulation estimate or an approved acceptance decision.
R17 | Community / neighbour disruption | Complaints, access restrictions or local disturbance may constrain site operations. | Stakeholder | Threat | 11% | Local | Duration | Noise, traffic or access conflict | Project Manager | Mitigate | Agree delivery routes and working-hour arrangements; appoint a neighbour liaison contact. | Monitoring | Fixed | Site logistics and external works ¦ V2.2 new assessments and responses are illustrative; original status/Active preserved as scenario attributes. | TRUE | 3 | 2 | ILLUSTRATIVE initial impact assessment: Neighbour or access restrictions can interrupt site logistics and extend rate-based costs. | Project Manager | Before A01 mobilisation | 7% | 2 | 2 | Pending | ILLUSTRATIVE post-response threat exposure; Early engagement reduces access restrictions and resulting time-related costs. Not a simulation estimate or an approved acceptance decision.
R18 | MEP coordination clash | Electrical, plumbing or HVAC routes may conflict and require redesign/rework. | Coordination | Threat | 23% | Local | Both | Insufficient multidisciplinary coordination | MEP Manager | Mitigate | Complete multidisciplinary clash checks and coordinated installation drawings before MEP release. | Open | Triangular | MEP rough-in and ceilings ¦ V2.2 new assessments and responses are illustrative; original status/Active preserved as scenario attributes. | TRUE | 4 | 4 | ILLUSTRATIVE initial impact assessment: MEP clashes can delay several service trades and require redesign or installation rework. | MEP Manager | Before A12 electrical rough-in | 12% | 3 | 3 | Pending | ILLUSTRATIVE post-response threat exposure; Resolved routing interfaces reduce installation rework, waiting and replacement materials. Not a simulation estimate or an approved acceptance decision.
R19 | Waterproofing failure | Waterproofing may fail testing and require removal and reapplication. | Quality | Threat | 13% | Local | Both | Poor substrate/application or detailing | QA/QC Manager | Mitigate | Approve substrate preparation, inspect detailing and conduct staged flood tests before finishes. | Monitoring | Beta-PERT | Wet areas and envelope ¦ V2.2 new assessments and responses are illustrative; original status/Active preserved as scenario attributes. | TRUE | 4 | 4 | ILLUSTRATIVE initial impact assessment: Waterproofing defects can hold finishes and require removal, replacement and repeat testing. | QA/QC Manager | Before A16 waterproofing | 7% | 3 | 3 | Pending | ILLUSTRATIVE post-response threat exposure; Staged acceptance reduces defects and confines removal/reapplication to smaller areas. Not a simulation estimate or an approved acceptance decision.
R20 | Commissioning failure | Systems may fail functional testing, causing troubleshooting and retesting. | Technical | Threat | 17% | Local | Both | Installation/configuration defects | Commissioning Manager | Mitigate | Approve commissioning procedures and perform pre-functional checks before integrated testing. | Open | Normal | Late-stage systems ¦ V2.2 new assessments and responses are illustrative; original status/Active preserved as scenario attributes. | TRUE | 4 | 3 | ILLUSTRATIVE initial impact assessment: Failed functional tests can delay handover and require troubleshooting and retesting. | Commissioning Manager | Before A27 commissioning | 10% | 3 | 2 | Pending | ILLUSTRATIVE post-response threat exposure; Prechecks reduce failures and troubleshooting/retest costs at final commissioning. Not a simulation estimate or an approved acceptance decision.
R21 | Prefabrication efficiency | Off-site fabrication may reduce installation duration and site waste. | Innovation | Opportunity | 18% | Local | Both | Successful prefabrication / modularization | Project Manager | Exploit | Confirm prefabrication tolerances, approve shop drawings and coordinate off-site fabrication with installation. | Monitoring | Fixed | MEP and joinery opportunity ¦ V2.2 new assessments and responses are illustrative; original status/Active preserved as scenario attributes. | TRUE | 3 | 3 | ILLUSTRATIVE initial impact assessment: Prefabrication can shorten installation and reduce waste in suitable MEP and joinery packages. | Project Manager | Before A12 MEP fabrication release | 28% | 4 | 4 | Pending | ILLUSTRATIVE post-response opportunity benefit; Prepared interfaces increase the chance and benefit of faster installation and reduced material waste. Not a simulation estimate or an approved acceptance decision.
R22 | Bulk-purchase discount | Consolidated procurement may reduce selected material costs. | Commercial | Opportunity | 25% | Global | Cost | Supplier volume discount | Procurement Manager | Exploit | Aggregate procurement quantities and negotiate volume-price agreements with approved suppliers. | Closed | Triangular | Cost opportunity ¦ V2.2 new assessments and responses are illustrative; original status/Active preserved as scenario attributes. | TRUE | 1 | 3 | ILLUSTRATIVE initial impact assessment: Volume purchasing can reduce material expenditure; no schedule benefit is mapped (minimum schedule class 1). | Procurement Manager | Before material package orders | 35% | 1 | 4 | Pending | ILLUSTRATIVE post-response opportunity benefit; Consolidated purchases increase discount likelihood and direct cost savings; no schedule saving is mapped. Not a simulation estimate or an approved acceptance decision.
R23 | Early design freeze | Timely closure of design decisions may reduce rework and improve flow. | Design | Opportunity | 20% | Local | Both | Strong design governance | Design Manager | Enhance | Obtain coordinated design sign-off and client decisions before downstream package release. | Open | Beta-PERT | Downstream execution benefit ¦ V2.2 new assessments and responses are illustrative; original status/Active preserved as scenario attributes. | TRUE | 4 | 3 | ILLUSTRATIVE initial impact assessment: Early coordinated design decisions can avoid downstream waiting, revisions and direct rework costs. | Design Manager | Before A07 structural frame | 30% | 4 | 4 | Pending | ILLUSTRATIVE post-response opportunity benefit; Earlier design closure increases avoided delay and direct redesign/rework savings. Not a simulation estimate or an approved acceptance decision.
R24 | Accelerated authority approval | Complete submissions and early engagement may shorten approval lead times. | Regulatory | Opportunity | 12% | Global | Duration | Effective authority coordination | Project Manager | Enhance | Hold an authority pre-submission meeting and submit a complete, checked approval package. | Monitoring | Normal | Final approval opportunity ¦ V2.2 new assessments and responses are illustrative; original status/Active preserved as scenario attributes. | TRUE | 3 | 1 | ILLUSTRATIVE initial impact assessment: Faster authority approval shortens handover lead time. A29 and A30 are fixed-fee examples, so no time-rate saving is modelled for those packages. | Project Manager | Before A29 final inspection | 22% | 4 | 1 | Pending | ILLUSTRATIVE opportunity benefit: complete early submissions increase the chance of shorter approval time. No time-rate cost saving is modelled for the fixed-fee final packages. Acceptance remains Pending.

## Risk_Activity_Map
4. Risk-Activity Mapping
Risk_ID | Activity_ID | Impact_Type | Distribution | Impact_Fixed | Impact_Min | Impact_MostLikely | Impact_Max | Impact_Mean | Impact_SD
R01 | A05 | Duration | Fixed | 1 | 0.25 | 0.75 | 2 | 1 | 0.25
R01 | A07 | Duration | Triangular | 1 | 0.25 | 0.75 | 2 | 1 | 0.25
R01 | A08 | Duration | Beta-PERT | 1 | 0.25 | 0.75 | 2 | 1 | 0.25
R01 | A09 | Duration | Uniform | 1 | 0.25 | 0.75 | 2 | 1 | 0.25
R01 | A15 | Duration | Normal | 1 | 0.25 | 0.75 | 2 | 1 | 0.25
R01 | A19 | Duration | Exponential | 1 | 0.25 | 0.75 | 2 | 1 | 0.25
R01 | A24 | Duration | Lognormal | 1 | 0.25 | 0.75 | 2 | 1 | 0.25
R02 | A07 | Duration | Gamma | 1 | 0.25 | 0.75 | 2 | 1 | 0.25
R02 | A08 | Duration | Fixed | 2
R02 | A10 | Duration | Triangular |  | 1 | 2 | 5
R02 | A11 | Duration | Beta-PERT |  | 1 | 3 | 6
R02 | A17 | Duration | Normal |  |  |  |  | 3 | 1
R02 | A18 | Duration | Fixed | 2
R02 | A19 | Duration | Triangular |  | 1 | 2 | 5
R02 | A21 | Duration | Beta-PERT |  | 1 | 3 | 6
R03 | A03 | Duration | Normal |  |  |  |  | 3 | 1
R03 | A04 | Duration | Fixed | 2
R03 | A05 | Duration | Triangular |  | 1 | 2 | 5
R03 | A07 | Duration | Beta-PERT |  | 1 | 3 | 6
R03 | A08 | Duration | Normal |  |  |  |  | 3 | 1
R03 | A09 | Duration | Fixed | 2
R03 | A18 | Duration | Triangular |  | 1 | 2 | 5
R03 | A25 | Duration | Beta-PERT |  | 1 | 3 | 6
R03 | A26 | Duration | Normal |  |  |  |  | 3 | 1
R04 | A04 | Duration | Fixed | 2
R04 | A05 | Duration | Triangular |  | 1 | 2 | 5
R04 | A06 | Duration | Beta-PERT |  | 1 | 3 | 6
R04 | A04 | Cost | Normal |  |  |  |  | 3 | 1
R04 | A05 | Cost | Fixed | 2
R05 | A10 | Duration | Triangular |  | 1 | 2 | 5
R05 | A11 | Duration | Beta-PERT |  | 1 | 3 | 6
R05 | A12 | Duration | Normal |  |  |  |  | 3 | 1
R05 | A13 | Duration | Fixed | 2
R05 | A14 | Duration | Triangular |  | 1 | 2 | 5
R05 | A17 | Duration | Beta-PERT |  | 1 | 3 | 6
R05 | A19 | Duration | Normal |  |  |  |  | 3 | 1
R05 | A20 | Duration | Fixed | 2
R05 | A21 | Duration | Triangular |  | 1 | 2 | 5
R05 | A24 | Duration | Beta-PERT |  | 1 | 3 | 6
R05 | A12 | Cost | Normal |  |  |  |  | 3 | 1
R05 | A13 | Cost | Fixed | 2
R05 | A14 | Cost | Triangular |  | 1 | 2 | 5
R05 | A19 | Cost | Beta-PERT |  | 1 | 3 | 6
R05 | A24 | Cost | Normal |  |  |  |  | 3 | 1
R06 | A05 | Duration | Fixed | 2
R06 | A16 | Duration | Triangular |  | 1 | 2 | 5
R06 | A27 | Duration | Beta-PERT |  | 1 | 3 | 6
R06 | A29 | Duration | Normal |  |  |  |  | 3 | 1
R07 | A07 | Duration | Fixed | 2
R07 | A08 | Duration | Triangular |  | 1 | 2 | 5
R07 | A12 | Duration | Beta-PERT |  | 1 | 3 | 6
R07 | A13 | Duration | Normal |  |  |  |  | 3 | 1
R07 | A14 | Duration | Fixed | 2
R07 | A17 | Duration | Triangular |  | 1 | 2 | 5
R07 | A18 | Duration | Beta-PERT |  | 1 | 3 | 6
R07 | A19 | Duration | Normal |  |  |  |  | 3 | 1
R07 | A20 | Duration | Fixed | 2
R07 | A21 | Duration | Triangular |  | 1 | 2 | 5
R07 | A22 | Duration | Beta-PERT |  | 1 | 3 | 6
R07 | A23 | Duration | Normal |  |  |  |  | 3 | 1
R07 | A24 | Duration | Fixed | 2
R07 | A07 | Cost | Triangular |  | 1 | 2 | 5
R07 | A08 | Cost | Beta-PERT |  | 1 | 3 | 6
R07 | A12 | Cost | Normal |  |  |  |  | 3 | 1
R07 | A13 | Cost | Fixed | 2
R07 | A14 | Cost | Triangular |  | 1 | 2 | 5
R08 | A03 | Duration | Beta-PERT |  | 1 | 3 | 6
R08 | A04 | Duration | Normal |  |  |  |  | 3 | 1
R08 | A05 | Duration | Fixed | 2
R08 | A07 | Duration | Triangular |  | 1 | 2 | 5
R08 | A08 | Duration | Beta-PERT |  | 1 | 3 | 6
R08 | A09 | Duration | Normal |  |  |  |  | 3 | 1
R08 | A25 | Duration | Fixed | 2
R08 | A03 | Cost | Triangular |  | 1 | 2 | 5
R08 | A04 | Cost | Beta-PERT |  | 1 | 3 | 6
R08 | A07 | Cost | Normal |  |  |  |  | 3 | 1
R08 | A08 | Cost | Fixed | 2
R09 | A05 | Cost | Triangular |  | 1 | 2 | 5
R09 | A07 | Cost | Beta-PERT |  | 1 | 3 | 6
R09 | A08 | Cost | Normal |  |  |  |  | 3 | 1
R09 | A09 | Cost | Fixed | 2
R09 | A10 | Cost | Triangular |  | 1 | 2 | 5
R09 | A12 | Cost | Beta-PERT |  | 1 | 3 | 6
R09 | A13 | Cost | Normal |  |  |  |  | 3 | 1
R09 | A14 | Cost | Fixed | 2
R09 | A15 | Cost | Triangular |  | 1 | 2 | 5
R09 | A19 | Cost | Beta-PERT |  | 1 | 3 | 6
R09 | A22 | Cost | Normal |  |  |  |  | 3 | 1
R09 | A23 | Cost | Fixed | 2
R09 | A24 | Cost | Triangular |  | 1 | 2 | 5
R10 | A07 | Duration | Beta-PERT |  | 1 | 3 | 6
R10 | A08 | Duration | Normal |  |  |  |  | 3 | 1
R10 | A10 | Duration | Fixed | 2
R10 | A12 | Duration | Triangular |  | 1 | 2 | 5
R10 | A13 | Duration | Beta-PERT |  | 1 | 3 | 6
R10 | A14 | Duration | Normal |  |  |  |  | 3 | 1
R10 | A17 | Duration | Fixed | 2
R10 | A18 | Duration | Triangular |  | 1 | 2 | 5
R10 | A19 | Duration | Beta-PERT |  | 1 | 3 | 6
R10 | A20 | Duration | Normal |  |  |  |  | 3 | 1
R10 | A21 | Duration | Fixed | 2
R10 | A24 | Duration | Triangular |  | 1 | 2 | 5
R10 | A25 | Duration | Beta-PERT |  | 1 | 3 | 6
R10 | A12 | Cost | Normal |  |  |  |  | 3 | 1
R10 | A13 | Cost | Fixed | 2
R10 | A14 | Cost | Triangular |  | 1 | 2 | 5
R10 | A18 | Cost | Beta-PERT |  | 1 | 3 | 6
R10 | A24 | Cost | Normal |  |  |  |  | 3 | 1
R10 | A25 | Cost | Fixed | 2
R11 | A05 | Duration | Triangular |  | 1 | 2 | 5
R11 | A06 | Duration | Beta-PERT |  | 1 | 3 | 6
R11 | A07 | Duration | Normal |  |  |  |  | 3 | 1
R11 | A08 | Duration | Fixed | 2
R11 | A09 | Duration | Triangular |  | 1 | 2 | 5
R11 | A10 | Duration | Beta-PERT |  | 1 | 3 | 6
R11 | A11 | Duration | Normal |  |  |  |  | 3 | 1
R11 | A12 | Duration | Fixed | 2
R11 | A13 | Duration | Triangular |  | 1 | 2 | 5
R11 | A14 | Duration | Beta-PERT |  | 1 | 3 | 6
R11 | A16 | Duration | Normal |  |  |  |  | 3 | 1
R11 | A17 | Duration | Fixed | 2
R11 | A18 | Duration | Triangular |  | 1 | 2 | 5
R11 | A19 | Duration | Beta-PERT |  | 1 | 3 | 6
R11 | A20 | Duration | Normal |  |  |  |  | 3 | 1
R11 | A21 | Duration | Fixed | 2
R11 | A22 | Duration | Triangular |  | 1 | 2 | 5
R11 | A23 | Duration | Beta-PERT |  | 1 | 3 | 6
R11 | A24 | Duration | Normal |  |  |  |  | 3 | 1
R11 | A25 | Duration | Fixed | 2
R11 | A05 | Cost | Triangular |  | 1 | 2 | 5
R11 | A07 | Cost | Beta-PERT |  | 1 | 3 | 6
R11 | A08 | Cost | Normal |  |  |  |  | 3 | 1
R11 | A16 | Cost | Fixed | 2
R11 | A19 | Cost | Triangular |  | 1 | 2 | 5
R11 | A21 | Cost | Beta-PERT |  | 1 | 3 | 6
R11 | A24 | Cost | Normal |  |  |  |  | 3 | 1
R12 | A03 | Duration | Fixed | 2
R12 | A04 | Duration | Triangular |  | 1 | 2 | 5
R12 | A05 | Duration | Beta-PERT |  | 1 | 3 | 6
R12 | A07 | Duration | Normal |  |  |  |  | 3 | 1
R12 | A08 | Duration | Fixed | 2
R12 | A09 | Duration | Triangular |  | 1 | 2 | 5
R12 | A15 | Duration | Beta-PERT |  | 1 | 3 | 6
R12 | A18 | Duration | Normal |  |  |  |  | 3 | 1
R12 | A25 | Duration | Fixed | 2
R12 | A05 | Cost | Triangular |  | 1 | 2 | 5
R12 | A07 | Cost | Beta-PERT |  | 1 | 3 | 6
R12 | A08 | Cost | Normal |  |  |  |  | 3 | 1
R12 | A09 | Cost | Fixed | 2
R13 | A12 | Duration | Triangular |  | 1 | 2 | 5
R13 | A13 | Duration | Beta-PERT |  | 1 | 3 | 6
R13 | A14 | Duration | Normal |  |  |  |  | 3 | 1
R13 | A25 | Duration | Fixed | 2
R13 | A12 | Cost | Triangular |  | 1 | 2 | 5
R13 | A13 | Cost | Beta-PERT |  | 1 | 3 | 6
R13 | A25 | Cost | Normal |  |  |  |  | 3 | 1
R14 | A15 | Duration | Fixed | 2
R14 | A18 | Duration | Triangular |  | 1 | 2 | 5
R14 | A19 | Duration | Beta-PERT |  | 1 | 3 | 6
R14 | A20 | Duration | Normal |  |  |  |  | 3 | 1
R14 | A21 | Duration | Fixed | 2
R14 | A22 | Duration | Triangular |  | 1 | 2 | 5
R14 | A23 | Duration | Beta-PERT |  | 1 | 3 | 6
R14 | A24 | Duration | Normal |  |  |  |  | 3 | 1
R15 | A05 | Duration | Fixed | 2
R15 | A07 | Duration | Triangular |  | 1 | 2 | 5
R15 | A08 | Duration | Beta-PERT |  | 1 | 3 | 6
R15 | A09 | Duration | Normal |  |  |  |  | 3 | 1
R15 | A12 | Duration | Fixed | 2
R15 | A13 | Duration | Triangular |  | 1 | 2 | 5
R15 | A14 | Duration | Beta-PERT |  | 1 | 3 | 6
R15 | A15 | Duration | Normal |  |  |  |  | 3 | 1
R15 | A19 | Duration | Fixed | 2
R15 | A24 | Duration | Triangular |  | 1 | 2 | 5
R15 | A25 | Duration | Beta-PERT |  | 1 | 3 | 6
R15 | A05 | Cost | Normal |  |  |  |  | 3 | 1
R15 | A07 | Cost | Fixed | 2
R15 | A08 | Cost | Triangular |  | 1 | 2 | 5
R15 | A12 | Cost | Beta-PERT |  | 1 | 3 | 6
R15 | A13 | Cost | Normal |  |  |  |  | 3 | 1
R15 | A14 | Cost | Fixed | 2
R15 | A19 | Cost | Triangular |  | 1 | 2 | 5
R15 | A24 | Cost | Beta-PERT |  | 1 | 3 | 6
R16 | A09 | Cost | Normal |  |  |  |  | 3 | 1
R16 | A12 | Cost | Fixed | 2
R16 | A13 | Cost | Triangular |  | 1 | 2 | 5
R16 | A15 | Cost | Beta-PERT |  | 1 | 3 | 6
R16 | A19 | Cost | Normal |  |  |  |  | 3 | 1
R16 | A22 | Cost | Fixed | 2
R16 | A23 | Cost | Triangular |  | 1 | 2 | 5
R16 | A24 | Cost | Beta-PERT |  | 1 | 3 | 6
R17 | A01 | Duration | Normal |  |  |  |  | 3 | 1
R17 | A03 | Duration | Fixed | 2
R17 | A09 | Duration | Triangular |  | 1 | 2 | 5
R17 | A18 | Duration | Beta-PERT |  | 1 | 3 | 6
R17 | A25 | Duration | Normal |  |  |  |  | 3 | 1
R17 | A26 | Duration | Fixed | 2
R18 | A12 | Duration | Triangular |  | 1 | 2 | 5
R18 | A13 | Duration | Beta-PERT |  | 1 | 3 | 6
R18 | A14 | Duration | Normal |  |  |  |  | 3 | 1
R18 | A17 | Duration | Fixed | 2
R18 | A20 | Duration | Triangular |  | 1 | 2 | 5
R18 | A22 | Duration | Beta-PERT |  | 1 | 3 | 6
R18 | A23 | Duration | Normal |  |  |  |  | 3 | 1
R18 | A27 | Duration | Fixed | 2
R18 | A12 | Cost | Triangular |  | 1 | 2 | 5
R18 | A13 | Cost | Beta-PERT |  | 1 | 3 | 6
R18 | A14 | Cost | Normal |  |  |  |  | 3 | 1
R18 | A20 | Cost | Fixed | 2
R19 | A16 | Duration | Triangular |  | 1 | 2 | 5
R19 | A19 | Duration | Beta-PERT |  | 1 | 3 | 6
R19 | A21 | Duration | Normal |  |  |  |  | 3 | 1
R19 | A16 | Cost | Fixed | 2
R19 | A19 | Cost | Triangular |  | 1 | 2 | 5
R20 | A22 | Duration | Beta-PERT |  | 1 | 3 | 6
R20 | A23 | Duration | Normal |  |  |  |  | 3 | 1
R20 | A27 | Duration | Fixed | 2
R20 | A28 | Duration | Triangular |  | 1 | 2 | 5
R20 | A22 | Cost | Beta-PERT |  | 1 | 3 | 6
R20 | A23 | Cost | Normal |  |  |  |  | 3 | 1
R20 | A27 | Cost | Fixed | 2
R21 | A12 | Duration | Triangular |  | 1 | 2 | 5
R21 | A13 | Duration | Beta-PERT |  | 1 | 3 | 6
R21 | A14 | Duration | Normal |  |  |  |  | 3 | 1
R21 | A22 | Duration | Fixed | 2
R21 | A23 | Duration | Triangular |  | 1 | 2 | 5
R21 | A24 | Duration | Beta-PERT |  | 1 | 3 | 6
R21 | A12 | Cost | Normal |  |  |  |  | 3 | 1
R21 | A13 | Cost | Fixed | 2
R21 | A14 | Cost | Triangular |  | 1 | 2 | 5
R21 | A24 | Cost | Beta-PERT |  | 1 | 3 | 6
R22 | A05 | Cost | Normal |  |  |  |  | 3 | 1
R22 | A07 | Cost | Fixed | 2
R22 | A08 | Cost | Triangular |  | 1 | 2 | 5
R22 | A09 | Cost | Beta-PERT |  | 1 | 3 | 6
R22 | A15 | Cost | Normal |  |  |  |  | 3 | 1
R22 | A19 | Cost | Fixed | 2
R22 | A22 | Cost | Triangular |  | 1 | 2 | 5
R22 | A23 | Cost | Beta-PERT |  | 1 | 3 | 6
R22 | A24 | Cost | Normal |  |  |  |  | 3 | 1
R23 | A10 | Duration | Fixed | 2
R23 | A11 | Duration | Triangular |  | 1 | 2 | 5
R23 | A12 | Duration | Beta-PERT |  | 1 | 3 | 6
R23 | A13 | Duration | Normal |  |  |  |  | 3 | 1
R23 | A14 | Duration | Fixed | 2
R23 | A17 | Duration | Triangular |  | 1 | 2 | 5
R23 | A19 | Duration | Beta-PERT |  | 1 | 3 | 6
R23 | A20 | Duration | Normal |  |  |  |  | 3 | 1
R23 | A21 | Duration | Fixed | 2
R23 | A24 | Duration | Triangular |  | 1 | 2 | 5
R23 | A12 | Cost | Beta-PERT |  | 1 | 3 | 6
R23 | A13 | Cost | Normal |  |  |  |  | 3 | 1
R23 | A14 | Cost | Fixed | 2
R23 | A19 | Cost | Triangular |  | 1 | 2 | 5
R23 | A24 | Cost | Beta-PERT |  | 1 | 3 | 6
R24 | A29 | Duration | Normal |  |  |  |  | 3 | 1

## Risk_Relationships
5. Optional Risk-Risk Relationships - Advanced / Future Layer
Parent_Risk | Child_Risk | Relationship_Type | Influence_Parameter | Active | Notes
R03 | R04 | Causes/Increases |  | FALSE | Prolonged rainfall can increase groundwater/ground-condition difficulty.
R05 | R18 | Causes/Increases |  | FALSE | Late design change can increase MEP coordination clashes.
R07 | R10 | Causes/Increases |  | FALSE | Labour scarcity can worsen subcontractor delivery performance.
R10 | R11 | Causes/Increases |  | FALSE | Underperformance can increase quality failures and rework.
R11 | R06 | Causes/Increases |  | FALSE | Nonconforming work can delay inspection acceptance.
R15 | R01 | Causes/Increases |  | FALSE | Cash-flow constraints can delay material release and delivery.
R18 | R20 | Causes/Increases |  | FALSE | Unresolved MEP clashes can increase commissioning failures.
R19 | R11 | Associated |  | FALSE | Waterproofing failure is a specific quality/rework mechanism.
R23 | R05 | Reduces |  | FALSE | Early design freeze can reduce late design changes.
R21 | R07 | Reduces |  | FALSE | Prefabrication can reduce site skilled-labour demand.
R24 | R06 | Reduces |  | FALSE | Effective authority engagement can reduce approval delays.

## Validation_Spec
Validation Specification
Area | Rule | Severity | Example Message | Action
Activities | Activity_ID must be unique and nonblank | Error | Duplicate Activity_ID: A03 | Stop simulation
Network | Every predecessor must reference an existing Activity_ID | Error | A07 references unknown predecessor A99 | Stop simulation
Network | Network must be acyclic | Error | Circular relationship detected | Stop simulation
Duration | Duration values must be non-negative | Error | A04 has negative duration | Stop simulation
3-point distributions | Min ≤ Most Likely ≤ Max | Error | A07: Most Likely (12) exceeds Max (9) | Stop simulation
Normal distribution | Mean required; SD must be > 0 | Error | A04: Normal SD must be > 0 | Stop simulation
Risk | Risk_ID must be unique and nonblank | Error | Duplicate Risk_ID: R02 | Stop simulation
Risk | Probability must be between 0 and 1 | Error | R03 probability = 1.30 | Stop simulation
Mapping | Risk_ID must exist in Risk_Register | Error | Mapping references unknown risk R09 | Stop simulation
Mapping | Activity_ID must exist in Activities | Error | R04 maps to unknown activity A18 | Stop simulation
Mapping | Impact parameters must match selected distribution | Error | R02/A04 missing triangular mode | Stop simulation
Optional fields | Blank optional values are permitted | Info | Owner not supplied for R05 | Continue
Text input | Trim leading/trailing spaces where safe | Info | ' A03 ' normalized to 'A03' | Normalize

## Risk_Portrait_Spec
Risk Portrait - Scenario Specification
Scenario | Active Risks | Meaning | ΔMean | ΔP50 | ΔP90
S0 | None | Activity uncertainty only; no tested discrete risks
S1 | R1 | Highest-ranked selected risk
S2 | R1 + R2 | Cumulative addition of second-ranked risk
S3 | R1 + R2 + R3 | Cumulative addition of third-ranked risk
S5 | Top 5 active risks | Concentrated high-priority exposure
ST | All active risks | Total project risk exposure
Interpretation
Simulation control

## Case_Summary
V2.2 residential construction demonstration case
Case characteristic | Representation | Teaching dimension | Options demonstrated | Interpretation
Activities | 30 interconnected construction activities | Scope | Local / Global | Local may affect one or several mapped activities; Global is project-wide.
Risks | 24 risks: threats and opportunities | Risk type | Threat / Opportunity | Allows adverse and beneficial uncertainty.
Scope | Local and Global only | Impact target | Duration / Cost / Both | Demonstrates schedule, cost and joint effects.
Activity distributions | Fixed, Triangular, Beta-PERT, Normal | Status | Open / Monitoring / Closed | Shows different risk lifecycle states.
Risk distributions | Fixed, Triangular, Beta-PERT, Normal | Activity uncertainty | 4 distributions | Balanced use across the 30 activities.
Threat responses | Avoid, Mitigate, Transfer, Accept | Risk response | 7 strategy labels | Threat and opportunity strategies are represented.
Opportunity responses | Exploit, Enhance, Share, Accept | Relationships | Inactive examples included | Dependency layer available without forcing it into the base run.

## Risk_Categories
Project risk category reference
Category | Definition
Commercial | Contract terms, claims, pricing and commercial arrangements.
Contractor | Contractor or subcontractor capability and delivery performance.
Coordination | Interfaces, communication and alignment between project participants.
Design | Design completeness, changes, errors and design decisions.
Environmental | Weather, environmental conditions and environmental constraints.
Equipment | Equipment availability, reliability and performance.
Financial | Funding, cash flow and access to financial resources.
Geotechnical | Ground, groundwater and subsurface conditions.
HSE | Health, safety and environmental protection during work.
Innovation | New methods, technology and opportunities for improved delivery.
Operational | Execution processes, work sequencing and site operations.
Quality | Conformance, defects, inspection and rework.
Regulatory | Permits, approvals and regulatory requirements.
Resource | Workforce capacity, skills and other resource availability.
Security | Theft, unauthorised access and site security.
Stakeholder | Stakeholder expectations, engagement and external acceptance.
Supply | Material procurement, supplier availability and delivery.
Technical | Engineering feasibility, technical systems and performance.

## Risk_Treatments
Treatment scenario assumptions
Risk_ID | Treated_Probability | Duration_Impact_Multiplier | Cost_Impact_Multiplier | Assumption_Rationale
R01 | 18% | 0.7 | 1 | ILLUSTRATIVE scenario assumption: Early procurement reduces delivery interruptions; remaining delays still generate time-related costs. Treatment implementation cost is not included.
R02 | 32% | 1.15 | 1 | ILLUSTRATIVE scenario assumption: Stable crews increase the likelihood and size of schedule benefits; rate-based costs fall with shorter durations. Treatment implementation cost is not included.
R03 | 35% | 0.7 | 1 | ILLUSTRATIVE scenario assumption: Controls reduce disruption severity; they do not change the probability of adverse weather. Treatment implementation cost is not included.
R04 | 18% | 0.6 | 0.75 | ILLUSTRATIVE scenario assumption: Investigation does not change ground conditions; preparedness reduces resulting delay and additional ground-treatment costs. Treatment implementation cost is not included.
R05 | 15% | 0.65 | 0.75 | ILLUSTRATIVE scenario assumption: Coordinated released drawings reduce late changes and associated redesign/rework. Treatment implementation cost is not included.
R06 | 9% | 0.7 | 1 | ILLUSTRATIVE scenario assumption: Earlier complete submissions reduce administrative waiting; future-stage inspection exposure remains modelled. Treatment implementation cost is not included.
R07 | 16% | 0.75 | 0.85 | ILLUSTRATIVE scenario assumption: Labour commitments reduce shortages; standby arrangements limit delay and recruitment premiums. Treatment implementation cost is not included.
R08 | 10% | 0.6 | 0.8 | ILLUSTRATIVE scenario assumption: Maintenance reduces breakdown likelihood; replacement arrangements reduce downtime and emergency costs. Treatment implementation cost is not included.
R09 | 28% | 1 | 0.65 | ILLUSTRATIVE scenario assumption: Market-price changes remain possible; purchasing arrangements reduce the exposed cost increment. Treatment implementation cost is not included.
R10 | 14% | 0.7 | 0.8 | ILLUSTRATIVE scenario assumption: Capability checks and recovery planning reduce delivery failure and incremental remedial costs. Treatment implementation cost is not included.
R11 | 12% | 0.65 | 0.7 | ILLUSTRATIVE scenario assumption: First-work approval and inspection reduce defects and limit the scope of direct rework. Treatment implementation cost is not included.
R12 | 5% | 0.8 | 0.85 | ILLUSTRATIVE scenario assumption: Controls reduce incident likelihood; severe consequences remain possible and require HSE review regardless of screening score. Treatment implementation cost is not included.
R13 | 7% | 0.65 | 0.75 | ILLUSTRATIVE scenario assumption: Early utility verification reduces clashes and resulting relocation/rework. Treatment implementation cost is not included.
R14 | 12% | 0.65 | 1 | ILLUSTRATIVE scenario assumption: Clear deadlines and escalation reduce approval waiting; indirect time costs remain. Treatment implementation cost is not included.
R15 | 10% | 0.7 | 0.8 | ILLUSTRATIVE scenario assumption: Payment readiness and liquidity buffers reduce disruption; financing and remobilisation costs remain possible. Treatment implementation cost is not included.
R16 | 5% | 1 | 0.75 | ILLUSTRATIVE scenario assumption: Security measures reduce loss likelihood and unrecovered replacement costs; no direct schedule consequence is mapped. Treatment implementation cost is not included.
R17 | 7% | 0.7 | 1 | ILLUSTRATIVE scenario assumption: Early engagement reduces access restrictions and resulting time-related costs. Treatment implementation cost is not included.
R18 | 12% | 0.6 | 0.65 | ILLUSTRATIVE scenario assumption: Resolved routing interfaces reduce installation rework, waiting and replacement materials. Treatment implementation cost is not included.
R19 | 7% | 0.65 | 0.65 | ILLUSTRATIVE scenario assumption: Staged acceptance reduces defects and confines removal/reapplication to smaller areas. Treatment implementation cost is not included.
R20 | 10% | 0.65 | 0.75 | ILLUSTRATIVE scenario assumption: Prechecks reduce failures and troubleshooting/retest costs at final commissioning. Treatment implementation cost is not included.
R21 | 28% | 1.2 | 1.15 | ILLUSTRATIVE scenario assumption: Prepared interfaces increase the chance and benefit of faster installation and reduced material waste. Treatment implementation cost is not included.
R22 | 35% | 1 | 1.15 | ILLUSTRATIVE scenario assumption: Consolidated purchases increase discount likelihood and direct cost savings; no schedule saving is mapped. Treatment implementation cost is not included.
R23 | 30% | 1.15 | 1.1 | ILLUSTRATIVE scenario assumption: Earlier design closure increases avoided delay and direct redesign/rework savings. Treatment implementation cost is not included.
R24 | 22% | 1.15 | 1 | ILLUSTRATIVE scenario assumption: complete early submissions increase the probability and magnitude of shorter approval time. Final approval/handover fees are fixed; no rate saving is assumed. Response implementation costs are excluded.

## Case_Assumptions
V2.2 illustrative activity cost assumptions
Activity_ID | Original_Base_Cost | Reference_Duration | Time_Dependent_Share | Fixed_Cost | Cost_Rate | Reference_Total | Basis | Cost_Association
A01 | 12000 | 5 | 35% | 7800 | 840 | 12000 | ILLUSTRATIVE fixed and resource-occupancy cost split; reference budget retained. | Fixed + time
A02 | 8000 | 4.6667 | 50% | 4000.01 | 857.14 | 7999.9967 | ILLUSTRATIVE fixed and resource-occupancy cost split; reference budget retained. | Fixed + time
A03 | 25000 | 4.3333 | 45% | 13750.02 | 2596.15 | 25000.0033 | ILLUSTRATIVE fixed and resource-occupancy cost split; reference budget retained. | Fixed + time
A04 | 18000 | 5 | 50% | 9000 | 1800 | 18000 | ILLUSTRATIVE fixed and resource-occupancy cost split; reference budget retained. | Fixed + time
A05 | 65000 | 5 | 30% | 45500 | 3900 | 65000 | ILLUSTRATIVE fixed and resource-occupancy cost split; reference budget retained. | Fixed + time
A06 | 38000 | 5 | 30% | 26600 | 2280 | 38000 | ILLUSTRATIVE fixed and resource-occupancy cost split; reference budget retained. | Fixed + time
A07 | 85000 | 5 | 35% | 55250 | 5950 | 85000 | ILLUSTRATIVE fixed and resource-occupancy cost split; reference budget retained. | Fixed + time
A08 | 82000 | 5 | 35% | 53300 | 5740 | 82000 | ILLUSTRATIVE fixed and resource-occupancy cost split; reference budget retained. | Fixed + time
A09 | 42000 | 7 | 25% | 31500 | 1500 | 42000 | ILLUSTRATIVE fixed and resource-occupancy cost split; reference budget retained. | Fixed + time
A10 | 50000 | 10.6667 | 40% | 30000 | 1875 | 50000 | ILLUSTRATIVE fixed and resource-occupancy cost split; reference budget retained. | Fixed + time
A11 | 32000 | 8.3333 | 45% | 17600 | 1728 | 32000 | ILLUSTRATIVE fixed and resource-occupancy cost split; reference budget retained. | Fixed + time
A12 | 35000 | 8 | 40% | 21000 | 1750 | 35000 | ILLUSTRATIVE fixed and resource-occupancy cost split; reference budget retained. | Fixed + time
A13 | 36000 | 8 | 40% | 21600 | 1800 | 36000 | ILLUSTRATIVE fixed and resource-occupancy cost split; reference budget retained. | Fixed + time
A14 | 28000 | 6.6667 | 35% | 18200 | 1470 | 28000 | ILLUSTRATIVE fixed and resource-occupancy cost split; reference budget retained. | Fixed + time
A15 | 45000 | 6.3333 | 15% | 45000 | 0 | 45000 | ILLUSTRATIVE fixed-price package/fee; ordinary duration variation does not change price. Explicit direct risk costs remain separate. | Fixed only
A16 | 22000 | 5 | 30% | 15400 | 1320 | 22000 | ILLUSTRATIVE fixed and resource-occupancy cost split; reference budget retained. | Fixed + time
A17 | 40000 | 9 | 45% | 22000 | 2000 | 40000 | ILLUSTRATIVE fixed and resource-occupancy cost split; reference budget retained. | Fixed + time
A18 | 48000 | 9.6667 | 40% | 28799.97 | 1986.21 | 48000 | ILLUSTRATIVE fixed and resource-occupancy cost split; reference budget retained. | Fixed + time
A19 | 52000 | 9.1667 | 35% | 33800.04 | 1985.45 | 51999.9983 | ILLUSTRATIVE fixed and resource-occupancy cost split; reference budget retained. | Fixed + time
A20 | 26000 | 6 | 45% | 14300 | 1950 | 26000 | ILLUSTRATIVE fixed and resource-occupancy cost split; reference budget retained. | Fixed + time
A21 | 38000 | 9 | 50% | 19000.01 | 2111.11 | 38000 | ILLUSTRATIVE fixed and resource-occupancy cost split; reference budget retained. | Fixed + time
A22 | 30000 | 6.3333 | 25% | 30000 | 0 | 30000 | ILLUSTRATIVE fixed-price package/fee; ordinary duration variation does not change price. Explicit direct risk costs remain separate. | Fixed only
A23 | 32000 | 6.1667 | 25% | 32000 | 0 | 32000 | ILLUSTRATIVE fixed-price package/fee; ordinary duration variation does not change price. Explicit direct risk costs remain separate. | Fixed only
A24 | 42000 | 8 | 20% | 42000 | 0 | 42000 | ILLUSTRATIVE fixed-price package/fee; ordinary duration variation does not change price. Explicit direct risk costs remain separate. | Fixed only
A25 | 55000 | 9 | 40% | 33000.04 | 2444.44 | 55000 | ILLUSTRATIVE fixed and resource-occupancy cost split; reference budget retained. | Fixed + time
A26 | 18000 | 5.3333 | 45% | 9900 | 1518.75 | 18000 | ILLUSTRATIVE fixed and resource-occupancy cost split; reference budget retained. | Fixed + time
A27 | 20000 | 6.3333 | 60% | 7999.98 | 1894.74 | 20000 | ILLUSTRATIVE fixed and resource-occupancy cost split; reference budget retained. | Fixed + time
A28 | 15000 | 5 | 50% | 7500 | 1500 | 15000 | ILLUSTRATIVE fixed and resource-occupancy cost split; reference budget retained. | Fixed + time
A29 | 10000 | 4.3333 | 30% | 10000 | 0 | 10000 | ILLUSTRATIVE fixed-price package/fee; ordinary duration variation does not change price. Explicit direct risk costs remain separate. | Fixed only
A30 | 8000 | 2.1667 | 50% | 8000 | 0 | 8000 | ILLUSTRATIVE fixed-price package/fee; ordinary duration variation does not change price. Explicit direct risk costs remain separate. | Fixed only