## README
Project Risk Analysis V2.2 input workbook
Purpose | Oriented probabilistic project risk analysis input template.
Workflow | Project → Activities → Risk Register → Risk–Activity Mapping → Validate → Simulate → Risk Portrait → Treatment
Green cells | Core/expected user inputs.
Grey cells | Optional or conditionally required inputs.
Probability | Enter as decimal between 0 and 1 (e.g., 0.30 = 30%).
Duration logic | For three-point distributions: Min/Optimistic ≤ Most Likely ≤ Max/Pessimistic.
Risk occurrence | A risk is sampled once per Monte Carlo iteration, then applied to all mapped activities.
Risk impacts | Consequences are defined in Risk_Activity_Map so the same risk can affect activities differently.
Advanced layer | Risk_Relationships is optional and reserved for later causal/dependency modelling.
Cost model | Fixed_Cost + Cost_Rate × final activity duration + direct mapped risk costs; total floored at zero.
Migration | V2.2 splits each original budget into illustrative fixed/time portions. Fixed_Cost + Cost_Rate × reference duration preserves the original amount; see Case_Assumptions.
Units | Cost_Rate is currency per project time unit. Fixed_Cost is duration-independent; direct risk costs exclude expenses already covered by Cost_Rate.
Register selection | Active=false retains a risk for management but excludes it from simulation. An unselected risk may have blank Probability; active risks require it.
Qualitative scale | User-assessed impact: 1 very low, 2 low, 3 moderate, 4 high, 5 very high. Define project-specific consequences in Assessment_Rationale.
Screening scores | App calculates Probability × impact separately for schedule and cost. Ordinal screening only; no automatic acceptance thresholds.
Response action | Write a concrete action, owner and due date. Existing strategy-only actions are preserved and flagged for completion.
Residual assessment | Residual fields document human assessment; they do not alter simulation inputs. Pending remains until the responsible person decides.
Treatment assumptions | Optional Risk_Treatments rows initialise app controls; blank probability retains original, blank multipliers mean 1. Only selected active risks are treated when Run is pressed.
Treatment dimensions | Duration multiplier changes mapped duration; direct cost multiplier changes mapped cost. Rate-based costs follow final duration automatically.
Category definitions | Risk_Categories preserves project categories. Complete their inclusion criteria; no automatic classification is implied.
Risk relationships | Inactive future layer; no risk propagation in this release.
Risk portrait | Every curve is total project duration for its risk subset. ST includes all active risks. Intermediate scenarios require calculation; ST reuses the main result.
Risk association | Risk importance uses Pearson occurrence/outcome correlation; activity cruciality uses Spearman duration/project-duration correlation. Undefined constant cases display zero.
Category convention | Risk_Categories provides editable working definitions, not an external standard. Choose the primary category and explain overlaps in Notes.
Case source | Case Study of a Residential Building Project.docx: source for the 30-activity/24-risk scenario and original targets. New numeric rates, ratings and treatment effectiveness are illustrative assumptions.
Units assumption | The source specifies generic time/monetary units. Use project time units and monetary units consistently; no real calendar or currency is asserted.
Relative deadlines | Response_Due_Date contains a relative construction milestone because no project start date is supplied. Replace with actual dates once a baseline calendar exists.
Cost basis | Case_Assumptions now calculates live reference duration, cost rate, fixed cost and reference total; Activities links to these results. Green cells are inputs; grey cost cells are calculated.
No double counting | Direct mapped costs are treated as incremental materials, repairs, penalties or emergency expenditure beyond ordinary rate-based resources. Review these boundaries with case experts.
Post-response assumptions | Residual_Probability equals the proposed treated probability; residual severity ratings are subjective expectations, not recalculated simulation results. All acceptance decisions remain Pending.
Opportunities | Higher treated probabilities or multipliers strengthen benefits. Residual opportunity impacts describe expected benefit potential rather than remaining threat severity.
Treatment selection | All 24 risks have proposed treatment assumptions. Only risks selected in the app are treated; there is no automatic implementation or optimisation. Response implementation costs are excluded.
Existing lifecycle statuses | Original Closed statuses and Active=true values are retained as case attributes. Active controls numerical inclusion; Closed does not automatically exclude a risk.
Cost target check | Original activity budgets total 1,057,000 monetary units versus the original 900,000 target. Both are retained; the example already exceeds its target before discrete risks.
Live cost workflow | Select Cost_Association in Activities. Edit Original_Base_Cost and Time_Dependent_Share in Case_Assumptions. Edit duration parameters in Activities. Linked formulas update fixed cost and cost rate.
Fixed only | Fixed only forces Cost_Rate=0 and Fixed_Cost=Original_Base_Cost. The time-dependent share is ignored. A15, A22, A23, A24, A29 and A30 are illustrative fixed-price packages/fees, not verified contract terms.
Cost rate formula | Mixed activity rate = ROUND(original budget × time-dependent share / reference duration, 2). Fixed cost = ROUND(original budget − rate × reference duration, 2). Reference total is fixed cost + rate × reference duration.
Formula and unit checks | A positive time-dependent share requires positive reference duration. Use share 0 or Fixed only for a zero-duration activity. Keep time units consistent.
Direct risk costs | Fixed only removes duration-rate costs; it does not remove explicit additional risk costs from Risk_Activity_Map. Remove or adjust those mappings where the contract transfers that financial exposure.
Saving before upload | Recalculate and save in Excel before uploading after edits. The app reads saved formula results. Do not replace linked cost formulas with typed values unless deliberately leaving this live workflow.

## Project
1. Project Information
Field | Value | Required? | Data Type | Validation Rule | Example | Simulation Role
Project_ID | P01 | Yes | Text | Nonblank | P01 | Simulation identifier
Project_Name | Residential Building Project - V2.2 illustrative case | Yes | Text | Nonblank | Building Project | Reporting/context
Description | Expanded classroom/research demonstration with a broader activity network, threat/opportunity register, and risk–activity exposure map. | No | Text | Optional | Residential construction | Context
Target_Duration | 150 | No | Number | Positive if entered | 120 | Probability of meeting duration target
Target_Cost | 900000 | No | Number | Non-negative if entered | 500000 | Probability of meeting cost target
Simulation_Iterations | 5000 | Yes | Integer | Integer > 0 | 5000 | Monte Carlo run count
Random_Seed | 42 | No | Integer | Integer if entered | 42 | Reproducibility / controlled comparisons
Time_Unit | project time units | Yes | Text | All durations and rates use this unit | days | Cost-rate interpretation
Currency | monetary units | Yes | Text | Use one currency consistently | BRL | Cost interpretation

## Activities
2. Activity Register
Activity_ID | Activity_Name | Predecessors | Duration_Model | Duration_Fixed | Duration_Min | Duration_MostLikely | Duration_Max | Duration_Mean | Duration_SD | Fixed_Cost | Cost_Rate | Cost_Association
A01 | Mobilization and site establishment |  | Fixed | 3 | [5 empty] | 7800 | 1400 | Fixed + time
A02 | Site survey and setting out | A01 | Triangular |  | 2 | 3 | 5 |  |  | 4000 | 1200 | Fixed + time
A03 | Site clearing and earthworks | A02 | Beta-PERT |  | 4 | 6 | 9 |  |  | 13750.03 | 1824.32 | Fixed + time
A04 | Excavation | A03 | Normal |  |  |  |  | 5 | 1 | 9000 | 1800 | Fixed + time
A05 | Foundation works | A04 | Fixed | 10 | [5 empty] | 45500 | 1950 | Fixed + time
A06 | Ground-floor slab | A05 | Triangular |  | 4 | 6 | 9 |  |  | 26600 | 1800 | Fixed + time
A07 | Structural frame – lower floors | A06 | Beta-PERT |  | 8 | 12 | 17 |  |  | 55249.95 | 2445.21 | Fixed + time
A08 | Structural frame – upper floors | A07 | Normal |  |  |  |  | 11 | 2 | 53300.01 | 2609.09 | Fixed + time
A09 | Roof structure and covering | A08 | Fixed | 7 | [5 empty] | 31500 | 1500 | Fixed + time
A10 | External masonry and partitions | A08 | Triangular |  | 7 | 10 | 15 |  |  | 30000 | 1875 | Fixed + time
A11 | Internal partitions | A08 | Beta-PERT |  | 6 | 8 | 12 |  |  | 17600 | 1728 | Fixed + time
A12 | Electrical rough-in | A10,A11 | Normal |  |  |  |  | 8 | 1.5 | 21000 | 1750 | Fixed + time
A13 | Plumbing rough-in | A10,A11 | Fixed | 8 | [5 empty] | 21600 | 1800 | Fixed + time
A14 | HVAC / ventilation rough-in | A10,A11 | Triangular |  | 4 | 6 | 10 |  |  | 18200 | 1470 | Fixed + time
A15 | External doors and windows | A09,A10 | Beta-PERT |  | 4 | 6 | 10 |  |  | 45000 | 0 | Fixed only
A16 | Waterproofing | A09,A13 | Normal |  |  |  |  | 5 | 1 | 15400 | 1320 | Fixed + time
A17 | Internal plastering | A12,A13,A14 | Fixed | 9 | [5 empty] | 22000 | 2000 | Fixed + time
A18 | External rendering / façade | A15 | Triangular |  | 6 | 9 | 14 |  |  | 28799.97 | 1986.21 | Fixed + time
A19 | Floor screed and tiling | A16,A17 | Beta-PERT |  | 6 | 9 | 13 |  |  | 33800.04 | 1985.45 | Fixed + time
A20 | Ceilings | A17 | Normal |  |  |  |  | 6 | 1 | 14300 | 1950 | Fixed + time
A21 | Painting | A18,A19,A20 | Fixed | 9 | [5 empty] | 19000.01 | 2111.11 | Fixed + time
A22 | Electrical fixtures and final connections | A19,A20 | Triangular |  | 4 | 6 | 9 |  |  | 30000 | 0 | Fixed only
A23 | Plumbing fixtures and sanitary installation | A19 | Beta-PERT |  | 4 | 6 | 9 |  |  | 32000 | 0 | Fixed only
A24 | Joinery and cabinetry | A19,A21 | Normal |  |  |  |  | 8 | 1.5 | 42000 | 0 | Fixed only
A25 | External works and drainage | A09 | Fixed | 9 | [5 empty] | 33000.04 | 2444.44 | Fixed + time
A26 | Landscaping | A25 | Triangular |  | 3 | 5 | 8 |  |  | 9900 | 1518.75 | Fixed + time
A27 | Testing and commissioning | A22,A23,A24 | Beta-PERT |  | 4 | 6 | 10 |  |  | 7999.98 | 1894.74 | Fixed + time
A28 | Defect correction / punch list | A21,A24,A27 | Normal |  |  |  |  | 5 | 1 | 7500 | 1500 | Fixed + time
A29 | Final inspection and approvals | A26,A28 | Triangular |  | 2 | 4 | 7 |  |  | 10000 | 0 | Fixed only
A30 | Handover and closeout | A29 | Beta-PERT |  | 1 | 2 | 4 |  |  | 8000 | 0 | Fixed only

## Risk_Register
3. Risk Register
Risk_ID | Risk_Name | Risk_Statement | Category | Risk_Type | Probability | Scope | Impact_Type | Trigger_Cause | Owner | Response_Strategy | Response_Action | Status | Impact_Distribution_Default | Notes | Active | Qualitative_Schedule_Impact | Qualitative_Cost_Impact | Assessment_Rationale | Response_Owner | Response_Due_Date | Residual_Probability | Residual_Schedule_Impact | Residual_Cost_Impact | Residual_Acceptance | Residual_Rationale
R01 | Critical material delivery delay | Critical structural or finishing materials may arrive later than required. | Supply | Threat | 30% | Local | Duration | Supplier disruption / logistics delay | Procurement Manager | Mitigate | Approve material submittals early; place long-lead orders and agree delivery tracking plus a backup supplier. | Open | Fixed | Affects material-dependent activities ¦ V2.2 new assessments and responses are illustrative; original status/Active preserved as scenario attributes. | TRUE | 4 | 3 | ILLUSTRATIVE initial impact assessment: Late critical deliveries can hold foundations, frames or enclosure; delay also increases rate-based costs. | Procurement Manager | Before A05 foundation works | 18% | 3 | 2 | Pending | ILLUSTRATIVE post-response threat exposure; Early procurement reduces delivery interruptions; remaining delays still generate time-related costs. Not a simulation estimate or an approved acceptance decision.
R02 | Higher crew productivity | Experienced crews may complete repetitive work faster than planned. | Operational | Opportunity | 22% | Local | Duration | Learning curve / stable workforce | Site Manager | Exploit | Assign stable experienced crews to repetitive work; use weekly productivity feedback and coaching. | Monitoring | Triangular | Schedule opportunity ¦ V2.2 new assessments and responses are illustrative; original status/Active preserved as scenario attributes. | TRUE | 3 | 2 | ILLUSTRATIVE initial impact assessment: Learning and stable crews can shorten repetitive work and reduce time-dependent resource costs. | Site Manager | Before A07 structural frame | 32% | 4 | 3 | Pending | ILLUSTRATIVE post-response opportunity benefit; Stable crews increase the likelihood and size of schedule benefits; rate-based costs fall with shorter durations. Not a simulation estimate or an approved acceptance decision.
R03 | Adverse weather | Heavy rainfall or extreme weather may interrupt outdoor works. | Environmental | Threat | 35% | Local | Duration | Seasonal weather conditions | Project Manager | Mitigate | Plan weather-sensitive work windows; provide temporary drainage and protective covers. | Monitoring | Beta-PERT | Primarily early and external works ¦ V2.2 new assessments and responses are illustrative; original status/Active preserved as scenario attributes. | TRUE | 4 | 3 | ILLUSTRATIVE initial impact assessment: Rain can interrupt multiple outdoor work packages and extend paid resource occupancy. | Project Manager | Before A03 earthworks | 35% | 3 | 2 | Pending | ILLUSTRATIVE post-response threat exposure; Controls reduce disruption severity; they do not change the probability of adverse weather. Not a simulation estimate or an approved acceptance decision.
R04 | Unforeseen ground conditions | Unexpected soil, groundwater or buried obstruction conditions may be encountered. | Geotechnical | Threat | 18% | Local | Both | Incomplete subsurface information | Civil Engineer | Mitigate | Complete targeted ground investigation, groundwater checks and a foundation contingency method. | Open | Normal | Foundation-stage exposure ¦ V2.2 new assessments and responses are illustrative; original status/Active preserved as scenario attributes. | TRUE | 5 | 5 | ILLUSTRATIVE initial impact assessment: Unknown ground or groundwater can disrupt substructure sequencing and require substantial additional treatment. | Civil Engineer | Before A04 excavation | 18% | 3 | 4 | Pending | ILLUSTRATIVE post-response threat exposure; Investigation does not change ground conditions; preparedness reduces resulting delay and additional ground-treatment costs. Not a simulation estimate or an approved acceptance decision.
R05 | Design change / late clarification | Late design revisions or unresolved details may cause rework or waiting. | Design | Threat | 25% | Local | Both | Client/design coordination changes | Design Manager | Mitigate | Close design RFIs before release; coordinate discipline reviews and enforce change control. | Open | Fixed | Can affect MEP and finishes ¦ V2.2 new assessments and responses are illustrative; original status/Active preserved as scenario attributes. | TRUE | 4 | 4 | ILLUSTRATIVE initial impact assessment: Late design decisions can hold several workstreams and require direct redesign or rework. | Design Manager | Before A07 structural frame | 15% | 3 | 3 | Pending | ILLUSTRATIVE post-response threat exposure; Coordinated released drawings reduce late changes and associated redesign/rework. Not a simulation estimate or an approved acceptance decision.
R06 | Permit or inspection delay | Required authority review or inspection may take longer than planned. | Regulatory | Threat | 15% | Local | Duration | Authority workload / nonconformance | Project Manager | Mitigate | Confirm inspection hold points, submission completeness and booking lead times with the authority. | Closed | Triangular | Late-stage and selected hold points ¦ V2.2 new assessments and responses are illustrative; original status/Active preserved as scenario attributes. | TRUE | 4 | 2 | ILLUSTRATIVE initial impact assessment: Inspection waiting can block hold points or handover; cost exposure is mainly time-related. | Project Manager | Before first mapped inspection hold point | 9% | 3 | 2 | Pending | ILLUSTRATIVE post-response threat exposure; Earlier complete submissions reduce administrative waiting; future-stage inspection exposure remains modelled. Not a simulation estimate or an approved acceptance decision.
R07 | Skilled labour shortage | Specialist or skilled labour may be unavailable when needed. | Resource | Threat | 24% | Local | Both | Labour market constraints | Site Manager | Mitigate | Secure trade labour commitments and cross-train backup crews before mobilisation of specialist trades. | Open | Beta-PERT | Structural, MEP and finishing trades ¦ V2.2 new assessments and responses are illustrative; original status/Active preserved as scenario attributes. | TRUE | 4 | 4 | ILLUSTRATIVE initial impact assessment: Scarce skilled crews can delay structural, MEP and finishing packages and increase recruitment or overtime costs. | Site Manager | Before A07 structural frame | 16% | 3 | 3 | Pending | ILLUSTRATIVE post-response threat exposure; Labour commitments reduce shortages; standby arrangements limit delay and recruitment premiums. Not a simulation estimate or an approved acceptance decision.
R08 | Equipment breakdown | Critical plant or construction equipment may fail unexpectedly. | Equipment | Threat | 16% | Local | Both | Mechanical failure / poor maintenance | Plant Manager | Mitigate | Implement preventive maintenance and reserve replacement plant with agreed call-out times. | Monitoring | Normal | Earthworks and lifting-intensive work ¦ V2.2 new assessments and responses are illustrative; original status/Active preserved as scenario attributes. | TRUE | 3 | 3 | ILLUSTRATIVE initial impact assessment: Plant failure can delay equipment-dependent work and require emergency replacement or repairs. | Plant Manager | Before A03 earthworks | 10% | 2 | 2 | Pending | ILLUSTRATIVE post-response threat exposure; Maintenance reduces breakdown likelihood; replacement arrangements reduce downtime and emergency costs. Not a simulation estimate or an approved acceptance decision.
R09 | Material price escalation | Prices of key materials may exceed the budget assumption. | Commercial | Threat | 28% | Global | Cost | Market inflation / exchange-rate pressure | Commercial Manager | Mitigate | Agree fixed-price supply windows and competitively source key material packages. | Monitoring | Fixed | Cost-only exposure ¦ V2.2 new assessments and responses are illustrative; original status/Active preserved as scenario attributes. | TRUE | 1 | 5 | ILLUSTRATIVE initial impact assessment: Material inflation directly affects the purchase budget; no direct duration impact is mapped (minimum schedule class 1). | Commercial Manager | Before A05 procurement commitments | 28% | 1 | 4 | Pending | ILLUSTRATIVE post-response threat exposure; Market-price changes remain possible; purchasing arrangements reduce the exposed cost increment. Not a simulation estimate or an approved acceptance decision.
R10 | Subcontractor underperformance | A subcontractor may deliver below planned productivity or quality. | Contractor | Threat | 22% | Local | Both | Capacity / management weakness | Contracts Manager | Mitigate | Prequalify subcontractors; agree measurable production targets and an escalation/recovery procedure. | Open | Triangular | Trade-package exposure ¦ V2.2 new assessments and responses are illustrative; original status/Active preserved as scenario attributes. | TRUE | 4 | 4 | ILLUSTRATIVE initial impact assessment: Poor subcontractor production or quality can delay successors and generate recovery expenditure. | Contracts Manager | Before subcontract package award | 14% | 3 | 3 | Pending | ILLUSTRATIVE post-response threat exposure; Capability checks and recovery planning reduce delivery failure and incremental remedial costs. Not a simulation estimate or an approved acceptance decision.
R11 | Quality failure and rework | Work may fail inspection or specification and require correction. | Quality | Threat | 20% | Local | Both | Workmanship / supervision failure | QA/QC Manager | Mitigate | Use approved mock-ups, inspection checklists and sign-off before covering completed work. | Open | Beta-PERT | Broad execution exposure ¦ V2.2 new assessments and responses are illustrative; original status/Active preserved as scenario attributes. | TRUE | 4 | 4 | ILLUSTRATIVE initial impact assessment: Failed work may require removal, replacement and repeat inspections, affecting duration and direct costs. | QA/QC Manager | Before A06 slab and subsequent trade work | 12% | 3 | 3 | Pending | ILLUSTRATIVE post-response threat exposure; First-work approval and inspection reduce defects and limit the scope of direct rework. Not a simulation estimate or an approved acceptance decision.
R12 | Safety incident | A recordable incident may interrupt work and generate investigation/corrective actions. | HSE | Threat | 10% | Global | Both | Unsafe act or condition | HSE Manager | Avoid | Eliminate unsafe work methods where practicable; enforce permits, induction and supervisor checks. | Monitoring | Normal | Higher exposure in structural/external works ¦ V2.2 new assessments and responses are illustrative; original status/Active preserved as scenario attributes. | TRUE | 5 | 5 | ILLUSTRATIVE initial impact assessment: A serious incident may stop work and cause severe human, legal and financial consequences; low probability does not make it acceptable. | HSE Manager | Before A01 mobilisation; maintain throughout works | 5% | 5 | 5 | Pending | ILLUSTRATIVE post-response threat exposure; Controls reduce incident likelihood; severe consequences remain possible and require HSE review regardless of screening score. Not a simulation estimate or an approved acceptance decision.
R13 | Utility service conflict | Existing or planned utilities may conflict with construction or connection works. | Technical | Threat | 12% | Local | Both | Incomplete utility records / coordination | MEP Manager | Mitigate | Verify buried-service records, survey interfaces and agree coordinated service routes. | Closed | Fixed | MEP and external works ¦ V2.2 new assessments and responses are illustrative; original status/Active preserved as scenario attributes. | TRUE | 3 | 3 | ILLUSTRATIVE initial impact assessment: Utility conflicts can block excavation or services and require relocation and reinstatement. | MEP Manager | Before A04 excavation and A12 MEP works | 7% | 2 | 2 | Pending | ILLUSTRATIVE post-response threat exposure; Early utility verification reduces clashes and resulting relocation/rework. Not a simulation estimate or an approved acceptance decision.
R14 | Client decision delay | Delayed approval of samples, finishes or changes may hold downstream work. | Stakeholder | Threat | 20% | Local | Duration | Slow client approvals | Project Manager | Mitigate | Agree a client decision schedule, named approvers and time limits for sample approvals. | Open | Triangular | Finishing activities ¦ V2.2 new assessments and responses are illustrative; original status/Active preserved as scenario attributes. | TRUE | 3 | 2 | ILLUSTRATIVE initial impact assessment: Slow client approvals can hold finishing releases and extend time-dependent costs. | Project Manager | Before A15 doors/windows and finishing releases | 12% | 2 | 2 | Pending | ILLUSTRATIVE post-response threat exposure; Clear deadlines and escalation reduce approval waiting; indirect time costs remain. Not a simulation estimate or an approved acceptance decision.
R15 | Cash-flow / payment delay | Delayed certification or payment may constrain procurement and subcontractor progress. | Financial | Threat | 14% | Global | Both | Payment processing / funding constraints | Commercial Manager | Mitigate | Prepare rolling cash-flow forecasts, submit complete payment claims and arrange a contingency funding facility. | Monitoring | Beta-PERT | Potentially broad project impact ¦ V2.2 new assessments and responses are illustrative; original status/Active preserved as scenario attributes. | TRUE | 4 | 4 | ILLUSTRATIVE initial impact assessment: Cash shortages can affect multiple suppliers and trades and add financing or remobilisation costs. | Commercial Manager | Before A01 mobilisation; review each payment cycle | 10% | 3 | 3 | Pending | ILLUSTRATIVE post-response threat exposure; Payment readiness and liquidity buffers reduce disruption; financing and remobilisation costs remain possible. Not a simulation estimate or an approved acceptance decision.
R16 | Theft or vandalism | Materials, tools or completed work may be lost or damaged. | Security | Threat | 9% | Local | Cost | Site security breach | Site Manager | Mitigate | Secure stores, record material issues and provide controlled access and night surveillance. | Closed | Normal | Storage and finishing exposure ¦ V2.2 new assessments and responses are illustrative; original status/Active preserved as scenario attributes. | TRUE | 1 | 3 | ILLUSTRATIVE initial impact assessment: Theft causes replacement costs; no direct schedule impact is mapped (minimum schedule class 1). | Site Manager | Before A01 site establishment | 5% | 1 | 2 | Pending | ILLUSTRATIVE post-response threat exposure; Security measures reduce loss likelihood and unrecovered replacement costs; no direct schedule consequence is mapped. Not a simulation estimate or an approved acceptance decision.
R17 | Community / neighbour disruption | Complaints, access restrictions or local disturbance may constrain site operations. | Stakeholder | Threat | 11% | Local | Duration | Noise, traffic or access conflict | Project Manager | Mitigate | Agree delivery routes and working-hour arrangements; appoint a neighbour liaison contact. | Monitoring | Fixed | Site logistics and external works ¦ V2.2 new assessments and responses are illustrative; original status/Active preserved as scenario attributes. | TRUE | 3 | 2 | ILLUSTRATIVE initial impact assessment: Neighbour or access restrictions can interrupt site logistics and extend rate-based costs. | Project Manager | Before A01 mobilisation | 7% | 2 | 2 | Pending | ILLUSTRATIVE post-response threat exposure; Early engagement reduces access restrictions and resulting time-related costs. Not a simulation estimate or an approved acceptance decision.
R18 | MEP coordination clash | Electrical, plumbing or HVAC routes may conflict and require redesign/rework. | Coordination | Threat | 23% | Local | Both | Insufficient multidisciplinary coordination | MEP Manager | Mitigate | Complete multidisciplinary clash checks and coordinated installation drawings before MEP release. | Open | Triangular | MEP rough-in and ceilings ¦ V2.2 new assessments and responses are illustrative; original status/Active preserved as scenario attributes. | TRUE | 4 | 4 | ILLUSTRATIVE initial impact assessment: MEP clashes can delay several service trades and require redesign or installation rework. | MEP Manager | Before A12 electrical rough-in | 12% | 3 | 3 | Pending | ILLUSTRATIVE post-response threat exposure; Resolved routing interfaces reduce installation rework, waiting and replacement materials. Not a simulation estimate or an approved acceptance decision.
R19 | Waterproofing failure | Waterproofing may fail testing and require removal and reapplication. | Quality | Threat | 13% | Local | Both | Poor substrate/application or detailing | QA/QC Manager | Mitigate | Approve substrate preparation, inspect detailing and conduct staged flood tests before finishes. | Monitoring | Beta-PERT | Wet areas and envelope ¦ V2.2 new assessments and responses are illustrative; original status/Active preserved as scenario attributes. | TRUE | 4 | 4 | ILLUSTRATIVE initial impact assessment: Waterproofing defects can hold finishes and require removal, replacement and repeat testing. | QA/QC Manager | Before A16 waterproofing | 7% | 3 | 3 | Pending | ILLUSTRATIVE post-response threat exposure; Staged acceptance reduces defects and confines removal/reapplication to smaller areas. Not a simulation estimate or an approved acceptance decision.
R20 | Commissioning failure | Systems may fail functional testing, causing troubleshooting and retesting. | Technical | Threat | 17% | Local | Both | Installation/configuration defects | Commissioning Manager | Mitigate | Approve commissioning procedures and perform pre-functional checks before integrated testing. | Open | Normal | Late-stage systems ¦ V2.2 new assessments and responses are illustrative; original status/Active preserved as scenario attributes. | TRUE | 4 | 3 | ILLUSTRATIVE initial impact assessment: Failed functional tests can delay handover and require troubleshooting and retesting. | Commissioning Manager | Before A27 commissioning | 10% | 3 | 2 | Pending | ILLUSTRATIVE post-response threat exposure; Prechecks reduce failures and troubleshooting/retest costs at final commissioning. Not a simulation estimate or an approved acceptance decision.
R21 | Prefabrication efficiency | Off-site fabrication may reduce installation duration and site waste. | Innovation | Opportunity | 18% | Local | Both | Successful prefabrication / modularization | Project Manager | Exploit | Confirm prefabrication tolerances, approve shop drawings and coordinate off-site fabrication with installation. | Monitoring | Fixed | MEP and joinery opportunity ¦ V2.2 new assessments and responses are illustrative; original status/Active preserved as scenario attributes. | TRUE | 3 | 3 | ILLUSTRATIVE initial impact assessment: Prefabrication can shorten installation and reduce waste in suitable MEP and joinery packages. | Project Manager | Before A12 MEP fabrication release | 28% | 4 | 4 | Pending | ILLUSTRATIVE post-response opportunity benefit; Prepared interfaces increase the chance and benefit of faster installation and reduced material waste. Not a simulation estimate or an approved acceptance decision.
R22 | Bulk-purchase discount | Consolidated procurement may reduce selected material costs. | Commercial | Opportunity | 25% | Global | Cost | Supplier volume discount | Procurement Manager | Exploit | Aggregate procurement quantities and negotiate volume-price agreements with approved suppliers. | Closed | Triangular | Cost opportunity ¦ V2.2 new assessments and responses are illustrative; original status/Active preserved as scenario attributes. | TRUE | 1 | 3 | ILLUSTRATIVE initial impact assessment: Volume purchasing can reduce material expenditure; no schedule benefit is mapped (minimum schedule class 1). | Procurement Manager | Before material package orders | 35% | 1 | 4 | Pending | ILLUSTRATIVE post-response opportunity benefit; Consolidated purchases increase discount likelihood and direct cost savings; no schedule saving is mapped. Not a simulation estimate or an approved acceptance decision.
R23 | Early design freeze | Timely closure of design decisions may reduce rework and improve flow. | Design | Opportunity | 20% | Local | Both | Strong design governance | Design Manager | Enhance | Obtain coordinated design sign-off and client decisions before downstream package release. | Open | Beta-PERT | Downstream execution benefit ¦ V2.2 new assessments and responses are illustrative; original status/Active preserved as scenario attributes. | TRUE | 4 | 3 | ILLUSTRATIVE initial impact assessment: Early coordinated design decisions can avoid downstream waiting, revisions and direct rework costs. | Design Manager | Before A07 structural frame | 30% | 4 | 4 | Pending | ILLUSTRATIVE post-response opportunity benefit; Earlier design closure increases avoided delay and direct redesign/rework savings. Not a simulation estimate or an approved acceptance decision.
R24 | Accelerated authority approval | Complete submissions and early engagement may shorten approval lead times. | Regulatory | Opportunity | 12% | Global | Duration | Effective authority coordination | Project Manager | Enhance | Hold an authority pre-submission meeting and submit a complete, checked approval package. | Monitoring | Normal | Final approval opportunity ¦ V2.2 new assessments and responses are illustrative; original status/Active preserved as scenario attributes. | TRUE | 3 | 1 | ILLUSTRATIVE initial impact assessment: Faster authority approval shortens handover lead time. A29 and A30 are fixed-fee examples, so no time-rate saving is modelled for those packages. | Project Manager | Before A29 final inspection | 22% | 4 | 1 | Pending | ILLUSTRATIVE opportunity benefit: complete early submissions increase the chance of shorter approval time. No time-rate cost saving is modelled for the fixed-fee final packages. Acceptance remains Pending.

## Risk_Activity_Map
4. Risk-Activity Mapping
Risk_ID | Activity_ID | Impact_Type | Distribution | Impact_Fixed | Impact_Min | Impact_MostLikely | Impact_Max | Impact_Mean | Impact_SD
R01 | A05 | Duration | Fixed | 2
R01 | A07 | Duration | Triangular |  | 1 | 2 | 5
R01 | A08 | Duration | Beta-PERT |  | 1 | 3 | 6
R01 | A09 | Duration | Normal |  |  |  |  | 3 | 1
R01 | A15 | Duration | Fixed | 2
R01 | A19 | Duration | Triangular |  | 1 | 2 | 5
R01 | A24 | Duration | Beta-PERT |  | 1 | 3 | 6
R02 | A07 | Duration | Normal |  |  |  |  | 3 | 1
R02 | A08 | Duration | Fixed | 2
R02 | A10 | Duration | Triangular |  | 1 | 2 | 5
R02 | A11 | Duration | Beta-PERT |  | 1 | 3 | 6
R02 | A17 | Duration | Normal |  |  |  |  | 3 | 1
R02 | A18 | Duration | Fixed | 2
R02 | A19 | Duration | Triangular |  | 1 | 2 | 5
R02 | A21 | Duration | Beta-PERT |  | 1 | 3 | 6
R03 | A03 | Duration | Normal |  |  |  |  | 3 | 1
R03 | A04 | Duration | Fixed | 2
R03 | A05 | Duration | Triangular |  | 1 | 2 | 5
R03 | A07 | Duration | Beta-PERT |  | 1 | 3 | 6
R03 | A08 | Duration | Normal |  |  |  |  | 3 | 1
R03 | A09 | Duration | Fixed | 2
R03 | A18 | Duration | Triangular |  | 1 | 2 | 5
R03 | A25 | Duration | Beta-PERT |  | 1 | 3 | 6
R03 | A26 | Duration | Normal |  |  |  |  | 3 | 1
R04 | A04 | Duration | Fixed | 2
R04 | A05 | Duration | Triangular |  | 1 | 2 | 5
R04 | A06 | Duration | Beta-PERT |  | 1 | 3 | 6
R04 | A04 | Cost | Normal |  |  |  |  | 3 | 1
R04 | A05 | Cost | Fixed | 2
R05 | A10 | Duration | Triangular |  | 1 | 2 | 5
R05 | A11 | Duration | Beta-PERT |  | 1 | 3 | 6
R05 | A12 | Duration | Normal |  |  |  |  | 3 | 1
R05 | A13 | Duration | Fixed | 2
R05 | A14 | Duration | Triangular |  | 1 | 2 | 5
R05 | A17 | Duration | Beta-PERT |  | 1 | 3 | 6
R05 | A19 | Duration | Normal |  |  |  |  | 3 | 1
R05 | A20 | Duration | Fixed | 2
R05 | A21 | Duration | Triangular |  | 1 | 2 | 5
R05 | A24 | Duration | Beta-PERT |  | 1 | 3 | 6
R05 | A12 | Cost | Normal |  |  |  |  | 3 | 1
R05 | A13 | Cost | Fixed | 2
R05 | A14 | Cost | Triangular |  | 1 | 2 | 5
R05 | A19 | Cost | Beta-PERT |  | 1 | 3 | 6
R05 | A24 | Cost | Normal |  |  |  |  | 3 | 1
R06 | A05 | Duration | Fixed | 2
R06 | A16 | Duration | Triangular |  | 1 | 2 | 5
R06 | A27 | Duration | Beta-PERT |  | 1 | 3 | 6
R06 | A29 | Duration | Normal |  |  |  |  | 3 | 1
R07 | A07 | Duration | Fixed | 2
R07 | A08 | Duration | Triangular |  | 1 | 2 | 5
R07 | A12 | Duration | Beta-PERT |  | 1 | 3 | 6
R07 | A13 | Duration | Normal |  |  |  |  | 3 | 1
R07 | A14 | Duration | Fixed | 2
R07 | A17 | Duration | Triangular |  | 1 | 2 | 5
R07 | A18 | Duration | Beta-PERT |  | 1 | 3 | 6
R07 | A19 | Duration | Normal |  |  |  |  | 3 | 1
R07 | A20 | Duration | Fixed | 2
R07 | A21 | Duration | Triangular |  | 1 | 2 | 5
R07 | A22 | Duration | Beta-PERT |  | 1 | 3 | 6
R07 | A23 | Duration | Normal |  |  |  |  | 3 | 1
R07 | A24 | Duration | Fixed | 2
R07 | A07 | Cost | Triangular |  | 1 | 2 | 5
R07 | A08 | Cost | Beta-PERT |  | 1 | 3 | 6
R07 | A12 | Cost | Normal |  |  |  |  | 3 | 1
R07 | A13 | Cost | Fixed | 2
R07 | A14 | Cost | Triangular |  | 1 | 2 | 5
R08 | A03 | Duration | Beta-PERT |  | 1 | 3 | 6
R08 | A04 | Duration | Normal |  |  |  |  | 3 | 1
R08 | A05 | Duration | Fixed | 2
R08 | A07 | Duration | Triangular |  | 1 | 2 | 5
R08 | A08 | Duration | Beta-PERT |  | 1 | 3 | 6
R08 | A09 | Duration | Normal |  |  |  |  | 3 | 1
R08 | A25 | Duration | Fixed | 2
R08 | A03 | Cost | Triangular |  | 1 | 2 | 5
R08 | A04 | Cost | Beta-PERT |  | 1 | 3 | 6
R08 | A07 | Cost | Normal |  |  |  |  | 3 | 1
R08 | A08 | Cost | Fixed | 2
R09 | A05 | Cost | Triangular |  | 1 | 2 | 5
R09 | A07 | Cost | Beta-PERT |  | 1 | 3 | 6
R09 | A08 | Cost | Normal |  |  |  |  | 3 | 1
R09 | A09 | Cost | Fixed | 2
R09 | A10 | Cost | Triangular |  | 1 | 2 | 5
R09 | A12 | Cost | Beta-PERT |  | 1 | 3 | 6
R09 | A13 | Cost | Normal |  |  |  |  | 3 | 1
R09 | A14 | Cost | Fixed | 2
R09 | A15 | Cost | Triangular |  | 1 | 2 | 5
R09 | A19 | Cost | Beta-PERT |  | 1 | 3 | 6
R09 | A22 | Cost | Normal |  |  |  |  | 3 | 1
R09 | A23 | Cost | Fixed | 2
R09 | A24 | Cost | Triangular |  | 1 | 2 | 5
R10 | A07 | Duration | Beta-PERT |  | 1 | 3 | 6
R10 | A08 | Duration | Normal |  |  |  |  | 3 | 1
R10 | A10 | Duration | Fixed | 2
R10 | A12 | Duration | Triangular |  | 1 | 2 | 5
R10 | A13 | Duration | Beta-PERT |  | 1 | 3 | 6
R10 | A14 | Duration | Normal |  |  |  |  | 3 | 1
R10 | A17 | Duration | Fixed | 2
R10 | A18 | Duration | Triangular |  | 1 | 2 | 5
R10 | A19 | Duration | Beta-PERT |  | 1 | 3 | 6
R10 | A20 | Duration | Normal |  |  |  |  | 3 | 1
R10 | A21 | Duration | Fixed | 2
R10 | A24 | Duration | Triangular |  | 1 | 2 | 5
R10 | A25 | Duration | Beta-PERT |  | 1 | 3 | 6
R10 | A12 | Cost | Normal |  |  |  |  | 3 | 1
R10 | A13 | Cost | Fixed | 2
R10 | A14 | Cost | Triangular |  | 1 | 2 | 5
R10 | A18 | Cost | Beta-PERT |  | 1 | 3 | 6
R10 | A24 | Cost | Normal |  |  |  |  | 3 | 1
R10 | A25 | Cost | Fixed | 2
R11 | A05 | Duration | Triangular |  | 1 | 2 | 5
R11 | A06 | Duration | Beta-PERT |  | 1 | 3 | 6
R11 | A07 | Duration | Normal |  |  |  |  | 3 | 1
R11 | A08 | Duration | Fixed | 2
R11 | A09 | Duration | Triangular |  | 1 | 2 | 5
R11 | A10 | Duration | Beta-PERT |  | 1 | 3 | 6
R11 | A11 | Duration | Normal |  |  |  |  | 3 | 1
R11 | A12 | Duration | Fixed | 2
R11 | A13 | Duration | Triangular |  | 1 | 2 | 5
R11 | A14 | Duration | Beta-PERT |  | 1 | 3 | 6
R11 | A16 | Duration | Normal |  |  |  |  | 3 | 1
R11 | A17 | Duration | Fixed | 2
R11 | A18 | Duration | Triangular |  | 1 | 2 | 5
R11 | A19 | Duration | Beta-PERT |  | 1 | 3 | 6
R11 | A20 | Duration | Normal |  |  |  |  | 3 | 1
R11 | A21 | Duration | Fixed | 2
R11 | A22 | Duration | Triangular |  | 1 | 2 | 5
R11 | A23 | Duration | Beta-PERT |  | 1 | 3 | 6
R11 | A24 | Duration | Normal |  |  |  |  | 3 | 1
R11 | A25 | Duration | Fixed | 2
R11 | A05 | Cost | Triangular |  | 1 | 2 | 5
R11 | A07 | Cost | Beta-PERT |  | 1 | 3 | 6
R11 | A08 | Cost | Normal |  |  |  |  | 3 | 1
R11 | A16 | Cost | Fixed | 2
R11 | A19 | Cost | Triangular |  | 1 | 2 | 5
R11 | A21 | Cost | Beta-PERT |  | 1 | 3 | 6
R11 | A24 | Cost | Normal |  |  |  |  | 3 | 1
R12 | A03 | Duration | Fixed | 2
R12 | A04 | Duration | Triangular |  | 1 | 2 | 5
R12 | A05 | Duration | Beta-PERT |  | 1 | 3 | 6
R12 | A07 | Duration | Normal |  |  |  |  | 3 | 1
R12 | A08 | Duration | Fixed | 2
R12 | A09 | Duration | Triangular |  | 1 | 2 | 5
R12 | A15 | Duration | Beta-PERT |  | 1 | 3 | 6
R12 | A18 | Duration | Normal |  |  |  |  | 3 | 1
R12 | A25 | Duration | Fixed | 2
R12 | A05 | Cost | Triangular |  | 1 | 2 | 5
R12 | A07 | Cost | Beta-PERT |  | 1 | 3 | 6
R12 | A08 | Cost | Normal |  |  |  |  | 3 | 1
R12 | A09 | Cost | Fixed | 2
R13 | A12 | Duration | Triangular |  | 1 | 2 | 5
R13 | A13 | Duration | Beta-PERT |  | 1 | 3 | 6
R13 | A14 | Duration | Normal |  |  |  |  | 3 | 1
R13 | A25 | Duration | Fixed | 2
R13 | A12 | Cost | Triangular |  | 1 | 2 | 5
R13 | A13 | Cost | Beta-PERT |  | 1 | 3 | 6
R13 | A25 | Cost | Normal |  |  |  |  | 3 | 1
R14 | A15 | Duration | Fixed | 2
R14 | A18 | Duration | Triangular |  | 1 | 2 | 5
R14 | A19 | Duration | Beta-PERT |  | 1 | 3 | 6
R14 | A20 | Duration | Normal |  |  |  |  | 3 | 1
R14 | A21 | Duration | Fixed | 2
R14 | A22 | Duration | Triangular |  | 1 | 2 | 5
R14 | A23 | Duration | Beta-PERT |  | 1 | 3 | 6
R14 | A24 | Duration | Normal |  |  |  |  | 3 | 1
R15 | A05 | Duration | Fixed | 2
R15 | A07 | Duration | Triangular |  | 1 | 2 | 5
R15 | A08 | Duration | Beta-PERT |  | 1 | 3 | 6
R15 | A09 | Duration | Normal |  |  |  |  | 3 | 1
R15 | A12 | Duration | Fixed | 2
R15 | A13 | Duration | Triangular |  | 1 | 2 | 5
R15 | A14 | Duration | Beta-PERT |  | 1 | 3 | 6
R15 | A15 | Duration | Normal |  |  |  |  | 3 | 1
R15 | A19 | Duration | Fixed | 2
R15 | A24 | Duration | Triangular |  | 1 | 2 | 5
R15 | A25 | Duration | Beta-PERT |  | 1 | 3 | 6
R15 | A05 | Cost | Normal |  |  |  |  | 3 | 1
R15 | A07 | Cost | Fixed | 2
R15 | A08 | Cost | Triangular |  | 1 | 2 | 5
R15 | A12 | Cost | Beta-PERT |  | 1 | 3 | 6
R15 | A13 | Cost | Normal |  |  |  |  | 3 | 1
R15 | A14 | Cost | Fixed | 2
R15 | A19 | Cost | Triangular |  | 1 | 2 | 5
R15 | A24 | Cost | Beta-PERT |  | 1 | 3 | 6
R16 | A09 | Cost | Normal |  |  |  |  | 3 | 1
R16 | A12 | Cost | Fixed | 2
R16 | A13 | Cost | Triangular |  | 1 | 2 | 5
R16 | A15 | Cost | Beta-PERT |  | 1 | 3 | 6
R16 | A19 | Cost | Normal |  |  |  |  | 3 | 1
R16 | A22 | Cost | Fixed | 2
R16 | A23 | Cost | Triangular |  | 1 | 2 | 5
R16 | A24 | Cost | Beta-PERT |  | 1 | 3 | 6
R17 | A01 | Duration | Normal |  |  |  |  | 3 | 1
R17 | A03 | Duration | Fixed | 2
R17 | A09 | Duration | Triangular |  | 1 | 2 | 5
R17 | A18 | Duration | Beta-PERT |  | 1 | 3 | 6
R17 | A25 | Duration | Normal |  |  |  |  | 3 | 1
R17 | A26 | Duration | Fixed | 2
R18 | A12 | Duration | Triangular |  | 1 | 2 | 5
R18 | A13 | Duration | Beta-PERT |  | 1 | 3 | 6
R18 | A14 | Duration | Normal |  |  |  |  | 3 | 1
R18 | A17 | Duration | Fixed | 2
R18 | A20 | Duration | Triangular |  | 1 | 2 | 5
R18 | A22 | Duration | Beta-PERT |  | 1 | 3 | 6
R18 | A23 | Duration | Normal |  |  |  |  | 3 | 1
R18 | A27 | Duration | Fixed | 2
R18 | A12 | Cost | Triangular |  | 1 | 2 | 5
R18 | A13 | Cost | Beta-PERT |  | 1 | 3 | 6
R18 | A14 | Cost | Normal |  |  |  |  | 3 | 1
R18 | A20 | Cost | Fixed | 2
R19 | A16 | Duration | Triangular |  | 1 | 2 | 5
R19 | A19 | Duration | Beta-PERT |  | 1 | 3 | 6
R19 | A21 | Duration | Normal |  |  |  |  | 3 | 1
R19 | A16 | Cost | Fixed | 2
R19 | A19 | Cost | Triangular |  | 1 | 2 | 5
R20 | A22 | Duration | Beta-PERT |  | 1 | 3 | 6
R20 | A23 | Duration | Normal |  |  |  |  | 3 | 1
R20 | A27 | Duration | Fixed | 2
R20 | A28 | Duration | Triangular |  | 1 | 2 | 5
R20 | A22 | Cost | Beta-PERT |  | 1 | 3 | 6
R20 | A23 | Cost | Normal |  |  |  |  | 3 | 1
R20 | A27 | Cost | Fixed | 2
R21 | A12 | Duration | Triangular |  | 1 | 2 | 5
R21 | A13 | Duration | Beta-PERT |  | 1 | 3 | 6
R21 | A14 | Duration | Normal |  |  |  |  | 3 | 1
R21 | A22 | Duration | Fixed | 2
R21 | A23 | Duration | Triangular |  | 1 | 2 | 5
R21 | A24 | Duration | Beta-PERT |  | 1 | 3 | 6
R21 | A12 | Cost | Normal |  |  |  |  | 3 | 1
R21 | A13 | Cost | Fixed | 2
R21 | A14 | Cost | Triangular |  | 1 | 2 | 5
R21 | A24 | Cost | Beta-PERT |  | 1 | 3 | 6
R22 | A05 | Cost | Normal |  |  |  |  | 3 | 1
R22 | A07 | Cost | Fixed | 2
R22 | A08 | Cost | Triangular |  | 1 | 2 | 5
R22 | A09 | Cost | Beta-PERT |  | 1 | 3 | 6
R22 | A15 | Cost | Normal |  |  |  |  | 3 | 1
R22 | A19 | Cost | Fixed | 2
R22 | A22 | Cost | Triangular |  | 1 | 2 | 5
R22 | A23 | Cost | Beta-PERT |  | 1 | 3 | 6
R22 | A24 | Cost | Normal |  |  |  |  | 3 | 1
R23 | A10 | Duration | Fixed | 2
R23 | A11 | Duration | Triangular |  | 1 | 2 | 5
R23 | A12 | Duration | Beta-PERT |  | 1 | 3 | 6
R23 | A13 | Duration | Normal |  |  |  |  | 3 | 1
R23 | A14 | Duration | Fixed | 2
R23 | A17 | Duration | Triangular |  | 1 | 2 | 5
R23 | A19 | Duration | Beta-PERT |  | 1 | 3 | 6
R23 | A20 | Duration | Normal |  |  |  |  | 3 | 1
R23 | A21 | Duration | Fixed | 2
R23 | A24 | Duration | Triangular |  | 1 | 2 | 5
R23 | A12 | Cost | Beta-PERT |  | 1 | 3 | 6
R23 | A13 | Cost | Normal |  |  |  |  | 3 | 1
R23 | A14 | Cost | Fixed | 2
R23 | A19 | Cost | Triangular |  | 1 | 2 | 5
R23 | A24 | Cost | Beta-PERT |  | 1 | 3 | 6
R24 | A29 | Duration | Normal |  |  |  |  | 3 | 1

## Risk_Relationships
5. Optional Risk-Risk Relationships - Advanced / Future Layer
Parent_Risk | Child_Risk | Relationship_Type | Influence_Parameter | Active | Notes
R03 | R04 | Causes/Increases |  | FALSE | Prolonged rainfall can increase groundwater/ground-condition difficulty.
R05 | R18 | Causes/Increases |  | FALSE | Late design change can increase MEP coordination clashes.
R07 | R10 | Causes/Increases |  | FALSE | Labour scarcity can worsen subcontractor delivery performance.
R10 | R11 | Causes/Increases |  | FALSE | Underperformance can increase quality failures and rework.
R11 | R06 | Causes/Increases |  | FALSE | Nonconforming work can delay inspection acceptance.
R15 | R01 | Causes/Increases |  | FALSE | Cash-flow constraints can delay material release and delivery.
R18 | R20 | Causes/Increases |  | FALSE | Unresolved MEP clashes can increase commissioning failures.
R19 | R11 | Associated |  | FALSE | Waterproofing failure is a specific quality/rework mechanism.
R23 | R05 | Reduces |  | FALSE | Early design freeze can reduce late design changes.
R21 | R07 | Reduces |  | FALSE | Prefabrication can reduce site skilled-labour demand.
R24 | R06 | Reduces |  | FALSE | Effective authority engagement can reduce approval delays.

## Validation_Spec
Validation Specification
Area | Rule | Severity | Example Message | Action
Activities | Activity_ID must be unique and nonblank | Error | Duplicate Activity_ID: A03 | Stop simulation
Network | Every predecessor must reference an existing Activity_ID | Error | A07 references unknown predecessor A99 | Stop simulation
Network | Network must be acyclic | Error | Circular relationship detected | Stop simulation
Duration | Duration values must be non-negative | Error | A04 has negative duration | Stop simulation
3-point distributions | Min ≤ Most Likely ≤ Max | Error | A07: Most Likely (12) exceeds Max (9) | Stop simulation
Normal distribution | Mean required; SD must be > 0 | Error | A04: Normal SD must be > 0 | Stop simulation
Risk | Risk_ID must be unique and nonblank | Error | Duplicate Risk_ID: R02 | Stop simulation
Risk | Probability must be between 0 and 1 | Error | R03 probability = 1.30 | Stop simulation
Mapping | Risk_ID must exist in Risk_Register | Error | Mapping references unknown risk R09 | Stop simulation
Mapping | Activity_ID must exist in Activities | Error | R04 maps to unknown activity A18 | Stop simulation
Mapping | Impact parameters must match selected distribution | Error | R02/A04 missing triangular mode | Stop simulation
Optional fields | Blank optional values are permitted | Info | Owner not supplied for R05 | Continue
Text input | Trim leading/trailing spaces where safe | Info | ' A03 ' normalized to 'A03' | Normalize

## Risk_Portrait_Spec
Risk Portrait - Scenario Specification
Scenario | Active Risks | Meaning | ΔMean | ΔP50 | ΔP90
S0 | None | Activity uncertainty only; no tested discrete risks
S1 | R1 | Highest-ranked selected risk
S2 | R1 + R2 | Cumulative addition of second-ranked risk
S3 | R1 + R2 + R3 | Cumulative addition of third-ranked risk
S5 | Top 5 active risks | Concentrated high-priority exposure
ST | All active risks | Total project risk exposure
Interpretation
Simulation control

## Case_Summary
V2.2 residential construction demonstration case
Case characteristic | Representation | Teaching dimension | Options demonstrated | Interpretation
Activities | 30 interconnected construction activities | Scope | Local / Global | Local may affect one or several mapped activities; Global is project-wide.
Risks | 24 risks: threats and opportunities | Risk type | Threat / Opportunity | Allows adverse and beneficial uncertainty.
Scope | Local and Global only | Impact target | Duration / Cost / Both | Demonstrates schedule, cost and joint effects.
Activity distributions | Fixed, Triangular, Beta-PERT, Normal | Status | Open / Monitoring / Closed | Shows different risk lifecycle states.
Risk distributions | Fixed, Triangular, Beta-PERT, Normal | Activity uncertainty | 4 distributions | Balanced use across the 30 activities.
Threat responses | Avoid, Mitigate, Transfer, Accept | Risk response | 7 strategy labels | Threat and opportunity strategies are represented.
Opportunity responses | Exploit, Enhance, Share, Accept | Relationships | Inactive examples included | Dependency layer available without forcing it into the base run.

## Risk_Categories
Project risk category reference
Category | Definition
Commercial | Contract terms, claims, pricing and commercial arrangements.
Contractor | Contractor or subcontractor capability and delivery performance.
Coordination | Interfaces, communication and alignment between project participants.
Design | Design completeness, changes, errors and design decisions.
Environmental | Weather, environmental conditions and environmental constraints.
Equipment | Equipment availability, reliability and performance.
Financial | Funding, cash flow and access to financial resources.
Geotechnical | Ground, groundwater and subsurface conditions.
HSE | Health, safety and environmental protection during work.
Innovation | New methods, technology and opportunities for improved delivery.
Operational | Execution processes, work sequencing and site operations.
Quality | Conformance, defects, inspection and rework.
Regulatory | Permits, approvals and regulatory requirements.
Resource | Workforce capacity, skills and other resource availability.
Security | Theft, unauthorised access and site security.
Stakeholder | Stakeholder expectations, engagement and external acceptance.
Supply | Material procurement, supplier availability and delivery.
Technical | Engineering feasibility, technical systems and performance.

## Risk_Treatments
Treatment scenario assumptions
Risk_ID | Treated_Probability | Duration_Impact_Multiplier | Cost_Impact_Multiplier | Assumption_Rationale
R01 | 18% | 0.7 | 1 | ILLUSTRATIVE scenario assumption: Early procurement reduces delivery interruptions; remaining delays still generate time-related costs. Treatment implementation cost is not included.
R02 | 32% | 1.15 | 1 | ILLUSTRATIVE scenario assumption: Stable crews increase the likelihood and size of schedule benefits; rate-based costs fall with shorter durations. Treatment implementation cost is not included.
R03 | 35% | 0.7 | 1 | ILLUSTRATIVE scenario assumption: Controls reduce disruption severity; they do not change the probability of adverse weather. Treatment implementation cost is not included.
R04 | 18% | 0.6 | 0.75 | ILLUSTRATIVE scenario assumption: Investigation does not change ground conditions; preparedness reduces resulting delay and additional ground-treatment costs. Treatment implementation cost is not included.
R05 | 15% | 0.65 | 0.75 | ILLUSTRATIVE scenario assumption: Coordinated released drawings reduce late changes and associated redesign/rework. Treatment implementation cost is not included.
R06 | 9% | 0.7 | 1 | ILLUSTRATIVE scenario assumption: Earlier complete submissions reduce administrative waiting; future-stage inspection exposure remains modelled. Treatment implementation cost is not included.
R07 | 16% | 0.75 | 0.85 | ILLUSTRATIVE scenario assumption: Labour commitments reduce shortages; standby arrangements limit delay and recruitment premiums. Treatment implementation cost is not included.
R08 | 10% | 0.6 | 0.8 | ILLUSTRATIVE scenario assumption: Maintenance reduces breakdown likelihood; replacement arrangements reduce downtime and emergency costs. Treatment implementation cost is not included.
R09 | 28% | 1 | 0.65 | ILLUSTRATIVE scenario assumption: Market-price changes remain possible; purchasing arrangements reduce the exposed cost increment. Treatment implementation cost is not included.
R10 | 14% | 0.7 | 0.8 | ILLUSTRATIVE scenario assumption: Capability checks and recovery planning reduce delivery failure and incremental remedial costs. Treatment implementation cost is not included.
R11 | 12% | 0.65 | 0.7 | ILLUSTRATIVE scenario assumption: First-work approval and inspection reduce defects and limit the scope of direct rework. Treatment implementation cost is not included.
R12 | 5% | 0.8 | 0.85 | ILLUSTRATIVE scenario assumption: Controls reduce incident likelihood; severe consequences remain possible and require HSE review regardless of screening score. Treatment implementation cost is not included.
R13 | 7% | 0.65 | 0.75 | ILLUSTRATIVE scenario assumption: Early utility verification reduces clashes and resulting relocation/rework. Treatment implementation cost is not included.
R14 | 12% | 0.65 | 1 | ILLUSTRATIVE scenario assumption: Clear deadlines and escalation reduce approval waiting; indirect time costs remain. Treatment implementation cost is not included.
R15 | 10% | 0.7 | 0.8 | ILLUSTRATIVE scenario assumption: Payment readiness and liquidity buffers reduce disruption; financing and remobilisation costs remain possible. Treatment implementation cost is not included.
R16 | 5% | 1 | 0.75 | ILLUSTRATIVE scenario assumption: Security measures reduce loss likelihood and unrecovered replacement costs; no direct schedule consequence is mapped. Treatment implementation cost is not included.
R17 | 7% | 0.7 | 1 | ILLUSTRATIVE scenario assumption: Early engagement reduces access restrictions and resulting time-related costs. Treatment implementation cost is not included.
R18 | 12% | 0.6 | 0.65 | ILLUSTRATIVE scenario assumption: Resolved routing interfaces reduce installation rework, waiting and replacement materials. Treatment implementation cost is not included.
R19 | 7% | 0.65 | 0.65 | ILLUSTRATIVE scenario assumption: Staged acceptance reduces defects and confines removal/reapplication to smaller areas. Treatment implementation cost is not included.
R20 | 10% | 0.65 | 0.75 | ILLUSTRATIVE scenario assumption: Prechecks reduce failures and troubleshooting/retest costs at final commissioning. Treatment implementation cost is not included.
R21 | 28% | 1.2 | 1.15 | ILLUSTRATIVE scenario assumption: Prepared interfaces increase the chance and benefit of faster installation and reduced material waste. Treatment implementation cost is not included.
R22 | 35% | 1 | 1.15 | ILLUSTRATIVE scenario assumption: Consolidated purchases increase discount likelihood and direct cost savings; no schedule saving is mapped. Treatment implementation cost is not included.
R23 | 30% | 1.15 | 1.1 | ILLUSTRATIVE scenario assumption: Earlier design closure increases avoided delay and direct redesign/rework savings. Treatment implementation cost is not included.
R24 | 22% | 1.15 | 1 | ILLUSTRATIVE scenario assumption: complete early submissions increase the probability and magnitude of shorter approval time. Final approval/handover fees are fixed; no rate saving is assumed. Response implementation costs are excluded.

## Case_Assumptions
V2.2 illustrative activity cost assumptions
Activity_ID | Original_Base_Cost | Reference_Duration | Time_Dependent_Share | Fixed_Cost | Cost_Rate | Reference_Total | Basis | Cost_Association
A01 | 12000 | 3 | 35% | 7800 | 1400 | 12000 | ILLUSTRATIVE fixed and resource-occupancy cost split; reference budget retained. | Fixed + time
A02 | 8000 | 3.3333 | 50% | 4000 | 1200 | 8000 | ILLUSTRATIVE fixed and resource-occupancy cost split; reference budget retained. | Fixed + time
A03 | 25000 | 6.1667 | 45% | 13750.03 | 1824.32 | 25000.0033 | ILLUSTRATIVE fixed and resource-occupancy cost split; reference budget retained. | Fixed + time
A04 | 18000 | 5 | 50% | 9000 | 1800 | 18000 | ILLUSTRATIVE fixed and resource-occupancy cost split; reference budget retained. | Fixed + time
A05 | 65000 | 10 | 30% | 45500 | 1950 | 65000 | ILLUSTRATIVE fixed and resource-occupancy cost split; reference budget retained. | Fixed + time
A06 | 38000 | 6.3333 | 30% | 26600 | 1800 | 38000 | ILLUSTRATIVE fixed and resource-occupancy cost split; reference budget retained. | Fixed + time
A07 | 85000 | 12.1667 | 35% | 55249.95 | 2445.21 | 85000.005 | ILLUSTRATIVE fixed and resource-occupancy cost split; reference budget retained. | Fixed + time
A08 | 82000 | 11 | 35% | 53300.01 | 2609.09 | 82000 | ILLUSTRATIVE fixed and resource-occupancy cost split; reference budget retained. | Fixed + time
A09 | 42000 | 7 | 25% | 31500 | 1500 | 42000 | ILLUSTRATIVE fixed and resource-occupancy cost split; reference budget retained. | Fixed + time
A10 | 50000 | 10.6667 | 40% | 30000 | 1875 | 50000 | ILLUSTRATIVE fixed and resource-occupancy cost split; reference budget retained. | Fixed + time
A11 | 32000 | 8.3333 | 45% | 17600 | 1728 | 32000 | ILLUSTRATIVE fixed and resource-occupancy cost split; reference budget retained. | Fixed + time
A12 | 35000 | 8 | 40% | 21000 | 1750 | 35000 | ILLUSTRATIVE fixed and resource-occupancy cost split; reference budget retained. | Fixed + time
A13 | 36000 | 8 | 40% | 21600 | 1800 | 36000 | ILLUSTRATIVE fixed and resource-occupancy cost split; reference budget retained. | Fixed + time
A14 | 28000 | 6.6667 | 35% | 18200 | 1470 | 28000 | ILLUSTRATIVE fixed and resource-occupancy cost split; reference budget retained. | Fixed + time
A15 | 45000 | 6.3333 | 15% | 45000 | 0 | 45000 | ILLUSTRATIVE fixed-price package/fee; ordinary duration variation does not change price. Explicit direct risk costs remain separate. | Fixed only
A16 | 22000 | 5 | 30% | 15400 | 1320 | 22000 | ILLUSTRATIVE fixed and resource-occupancy cost split; reference budget retained. | Fixed + time
A17 | 40000 | 9 | 45% | 22000 | 2000 | 40000 | ILLUSTRATIVE fixed and resource-occupancy cost split; reference budget retained. | Fixed + time
A18 | 48000 | 9.6667 | 40% | 28799.97 | 1986.21 | 48000 | ILLUSTRATIVE fixed and resource-occupancy cost split; reference budget retained. | Fixed + time
A19 | 52000 | 9.1667 | 35% | 33800.04 | 1985.45 | 51999.9983 | ILLUSTRATIVE fixed and resource-occupancy cost split; reference budget retained. | Fixed + time
A20 | 26000 | 6 | 45% | 14300 | 1950 | 26000 | ILLUSTRATIVE fixed and resource-occupancy cost split; reference budget retained. | Fixed + time
A21 | 38000 | 9 | 50% | 19000.01 | 2111.11 | 38000 | ILLUSTRATIVE fixed and resource-occupancy cost split; reference budget retained. | Fixed + time
A22 | 30000 | 6.3333 | 25% | 30000 | 0 | 30000 | ILLUSTRATIVE fixed-price package/fee; ordinary duration variation does not change price. Explicit direct risk costs remain separate. | Fixed only
A23 | 32000 | 6.1667 | 25% | 32000 | 0 | 32000 | ILLUSTRATIVE fixed-price package/fee; ordinary duration variation does not change price. Explicit direct risk costs remain separate. | Fixed only
A24 | 42000 | 8 | 20% | 42000 | 0 | 42000 | ILLUSTRATIVE fixed-price package/fee; ordinary duration variation does not change price. Explicit direct risk costs remain separate. | Fixed only
A25 | 55000 | 9 | 40% | 33000.04 | 2444.44 | 55000 | ILLUSTRATIVE fixed and resource-occupancy cost split; reference budget retained. | Fixed + time
A26 | 18000 | 5.3333 | 45% | 9900 | 1518.75 | 18000 | ILLUSTRATIVE fixed and resource-occupancy cost split; reference budget retained. | Fixed + time
A27 | 20000 | 6.3333 | 60% | 7999.98 | 1894.74 | 20000 | ILLUSTRATIVE fixed and resource-occupancy cost split; reference budget retained. | Fixed + time
A28 | 15000 | 5 | 50% | 7500 | 1500 | 15000 | ILLUSTRATIVE fixed and resource-occupancy cost split; reference budget retained. | Fixed + time
A29 | 10000 | 4.3333 | 30% | 10000 | 0 | 10000 | ILLUSTRATIVE fixed-price package/fee; ordinary duration variation does not change price. Explicit direct risk costs remain separate. | Fixed only
A30 | 8000 | 2.1667 | 50% | 8000 | 0 | 8000 | ILLUSTRATIVE fixed-price package/fee; ordinary duration variation does not change price. Explicit direct risk costs remain separate. | Fixed only